## Sheet1
Sprint | Sprint_Name | Theme | Status | Start_Date | End_Date | Completion_% | Feature | Sub_Feature | Task | Story_Points | Priority | Owner | Deliverable | Notes
1 | Core Architecture | Foundation Setup | COMPLETE | 2026-01-06 | 2026-01-20 | 100% | App Structure | Constants & Config | Define app metadata and validation limits | 3 | CRITICAL | Mark | app_constants.dart | Production Ready
1 | Core Architecture | Foundation Setup | COMPLETE | 2026-01-06 | 2026-01-20 | 100% | App Structure | Database Schema | Design & implement 10-table schema with migrations | 5 | CRITICAL | Mark | database_service.dart | Foreign keys enforced - 10 tables with proper indexes
1 | Core Architecture | Foundation Setup | COMPLETE | 2026-01-06 | 2026-01-20 | 100% | Navigation System | Router Setup | Implement GoRouter with 10+ route configurations | 5 | CRITICAL | Mark | app_router.dart | Auth guards working - redirect logic tested
1 | Core Architecture | Foundation Setup | COMPLETE | 2026-01-06 | 2026-01-20 | 100% | Theme System | Light/Dark Mode | Material 3 theme with persistence | 3 | HIGH | Mark | app_theme.dart | Theme toggle working - SharedPreferences persistence
1 | Core Architecture | Foundation Setup | COMPLETE | 2026-01-06 | 2026-01-20 | 100% | Error Handling | Exception Classes | Define custom exception hierarchy | 2 | MEDIUM | Mark | app_exceptions.dart | All layers covered - Auth DB Utils exceptions
1 | Core Architecture | Foundation Setup | COMPLETE | 2026-01-06 | 2026-01-20 | 100% | Utilities | Validators | Email/password/phone/URL validators | 2 | MEDIUM | Mark | validators.dart | Regex patterns tested - security hardened
1 | Core Architecture | Foundation Setup | COMPLETE | 2026-01-06 | 2026-01-20 | 100% | Data Models | User Model | Implement User model with 13 fields + serialization | 3 | CRITICAL | Mark | user_model.dart | Immutable design - copyWith pattern
2 | Authentication | User Auth | COMPLETE | 2026-01-21 | 2026-02-03 | 100% | Authentication | User Registration | Implement secure registration with validation | 5 | CRITICAL | Mark | auth_service.dart | SHA-256 hashing - salt added for security
2 | Authentication | User Auth | COMPLETE | 2026-01-21 | 2026-02-03 | 100% | Authentication | User Login | Implement login with password verification | 5 | CRITICAL | Mark | auth_service.dart | Constant-time comparison - timing attack resistant
2 | Authentication | User Auth | COMPLETE | 2026-01-21 | 2026-02-03 | 100% | State Management | Auth Provider | Reactive AuthProvider for login state | 3 | HIGH | Mark | auth_provider.dart | Session persistence - 7 methods implemented
2 | Authentication | User Auth | COMPLETE | 2026-01-21 | 2026-02-03 | 100% | UI | Login Screen | Build login form with validation | 3 | HIGH | Mark | login_screen.dart | Error snackbars - real-time validation feedback
2 | Authentication | User Auth | COMPLETE | 2026-01-21 | 2026-02-03 | 100% | UI | Register Screen | Build registration form with validations | 3 | HIGH | Mark | register_screen.dart | Email uniqueness check - all fields required
2 | Authentication | User Auth | COMPLETE | 2026-01-21 | 2026-02-03 | 100% | UI | Profile Setup | Profile setup screen after registration | 3 | MEDIUM | Mark | profile_setup_screen.dart | Avatar upload ready - image picker integrated
2 | Authentication | User Auth | COMPLETE | 2026-01-21 | 2026-02-03 | 100% | Role Management | Multi-Role System | Implement student/teacher/admin/coordinator roles | 2 | MEDIUM | Mark | user_model.dart | Seeded test accounts - 4 roles supported
3 | Portfolio & Projects | Content Creation | COMPLETE | 2026-02-04 | 2026-02-24 | 100% | Portfolio | Portfolio CRUD | Full Create/Read/Update/Delete functionality | 5 | CRITICAL | Mark | portfolio_repository.dart | Parameterized queries - SQL injection protected
3 | Portfolio & Projects | Content Creation | COMPLETE | 2026-02-04 | 2026-02-24 | 100% | Projects | Project CRUD | Full Create/Read/Update/Delete functionality | 5 | CRITICAL | Mark | project_repository.dart | Image path serialization - 16 fields managed
3 | Portfolio & Projects | Content Creation | COMPLETE | 2026-02-04 | 2026-02-24 | 100% | Image Management | Image Upload | Image picker integration with validation | 3 | HIGH | Mark | project_image_service.dart | 5MB limit enforced - quality 85 compression
3 | Portfolio & Projects | Content Creation | COMPLETE | 2026-02-04 | 2026-02-24 | 100% | Image Management | Image Gallery | Hero animation & swipe navigation | 3 | MEDIUM | Mark | project_detail_screen.dart | Smooth animations - pinch zoom supported
3 | Portfolio & Projects | Content Creation | COMPLETE | 2026-02-04 | 2026-02-24 | 100% | State Management | Portfolio Provider | Reactive portfolio state management | 3 | HIGH | Mark | portfolio_provider.dart | Immediate UI updates - notifyListeners called
3 | Portfolio & Projects | Content Creation | COMPLETE | 2026-02-04 | 2026-02-24 | 100% | UI | Portfolio Screens | List/detail/edit screens for portfolios | 4 | HIGH | Mark | portfolio_screen.dart | Responsive design - Material 3 cards
3 | Portfolio & Projects | Content Creation | COMPLETE | 2026-02-04 | 2026-02-24 | 100% | UI | Project Screens | Add/edit/detail screens for projects | 4 | HIGH | Mark | project_detail_screen.dart | Form validation - all inputs validated
4 | Certifications & Resume | Professional Info | COMPLETE | 2026-02-25 | 2026-03-23 | 85% | Certifications | Cert Model & Repository | 14-field model + full CRUD operations | 3 | CRITICAL | Mark | certification_repository.dart | Migration 5 ready - expiry date supported
4 | Certifications & Resume | Professional Info | COMPLETE | 2026-02-25 | 2026-03-23 | 85% | Certificates | Cert Image Upload | Image picker with 500KB limit validation | 2 | HIGH | Mark | cert_image_service.dart | File cleanup on update - unique filenames
4 | Certifications & Resume | Professional Info | COMPLETE | 2026-02-25 | 2026-03-23 | 85% | Certificates | Cert Provider | Reactive state with search & filtering | 3 | HIGH | Mark | certification_provider.dart | Real-time search works - sort order maintained
4 | Certifications & Resume | Professional Info | COMPLETE | 2026-02-25 | 2026-03-23 | 85% | Skills | Skills Model & Repository | Proficiency levels + skill management | 3 | HIGH | Mark | skill_repository.dart | Full CRUD operations - 6 proficiency levels
4 | Certifications & Resume | Professional Info | COMPLETE | 2026-02-25 | 2026-03-23 | 85% | Skills | Skills Provider | Reactive skills state management | 2 | MEDIUM | Mark | skills_provider.dart | Search filtering - all providers centralized
4 | Certifications & Resume | Professional Info | COMPLETE | 2026-02-25 | 2026-03-23 | 85% | Job Alignment | Job Matching Engine | Scoring algorithm (skills/exp/location/edu/certs) | 5 | CRITICAL | Mark | job_matching_service.dart | Weights: 40/25/15/10/10 - 8 seed jobs tested
4 | Certifications & Resume | Professional Info | COMPLETE | 2026-02-25 | 2026-03-23 | 85% | Job Alignment | Job Feed Provider | Load jobs with alignment scoring | 4 | CRITICAL | Mark | job_feed_provider.dart | Empty profile handles - threshold 0.15 set
4 | Certifications & Resume | Professional Info | COMPLETE | 2026-02-25 | 2026-03-23 | 85% | Jobs | Job Display | Show jobs on dashboard with search | 4 | HIGH | Mark | dashboard_screen.dart | Search bar added - real-time filtering working
4 | Certifications & Resume | Professional Info | COMPLETE | 2026-02-25 | 2026-03-23 | 85% | UI | Dashboard Enhancement | Jobs section + alignment badges + search | 4 | MEDIUM | Mark | dashboard_screen.dart | Color-coded badges - Green/Blue/Orange/Red
4 | Certifications & Resume | Professional Info | COMPLETE | 2026-02-25 | 2026-03-23 | 85% | Experience | Experience Form | Add/edit/delete work experience entries | 3 | MEDIUM | Mark | experience_screen.dart | In progress - model designed
4 | Certifications & Resume | Professional Info | COMPLETE | 2026-02-25 | 2026-03-23 | 85% | Education | Education Form | Add/edit/delete education entries | 3 | MEDIUM | Mark | education_screen.dart | In progress - model designed
4 | Certifications & Resume | Professional Info | COMPLETE | 2026-02-25 | 2026-03-23 | 85% | Code Quality | Provider Registry | Centralized provider setup in AppProviderRegistry | 2 | LOW | Mark | app_providers.dart | 30+ lines reduced from main.dart - cleaner
4 | Certifications & Resume | Professional Info | COMPLETE | 2026-02-25 | 2026-03-23 | 85% | Code Quality | Theme Widget | Reusable theme toggle widget | 1 | LOW | Mark | theme_toggle_button.dart | Eliminated duplication - DRY principle enforced
4 | Certifications & Resume | Professional Info | COMPLETE | 2026-02-25 | 2026-03-23 | 85% | Performance | APK Build | Universal APK 57.8MB (all architectures) | 3 | HIGH | Mark | build/app/outputs/flutter-apk/app-release.apk | Production ready - all ABI support