## Master Roadmap
Task No. | Description | Duration (hours) | Assignee | Prerequisite
Sprint 1: Foundation & Architecture
PFPH-1 | Flutter project init, pubspec.yaml, all package setup | 4 hrs. | Tom Kyle B. Caballegan | None
PFPH-2 | Enforce folder structure — create ALL placeholder .dart files | 3 hrs. | Tom Kyle B. Caballegan | PFPH-1
PFPH-3 | SQLite schema design — all 10 tables, ERD sign-off | 8 hrs. | Mark Leannie Gacutno | None
PFPH-4 | DatabaseService singleton: open(), close(), getDatabase(), migrations | 6 hrs. | Mark Leannie Gacutno | PFPH-3
PFPH-5 | AppRouter (GoRouter) — define ALL named routes upfront | 5 hrs. | Rex Bernard G. Gabor | PFPH-1
PFPH-6 | Bottom navigation scaffold + 5 placeholder tab screens | 6 hrs. | Rex Bernard G. Gabor | PFPH-5
PFPH-7 | Splash screen: logo + loading + session check → redirect | 4 hrs. | Tom Kyle B. Caballegan | PFPH-1
PFPH-8 | AppConstants: colors, font sizes, padding, DB name, version | 3 hrs. | Mark Leannie Gacutno | PFPH-1
PFPH-9 | AppTheme: Material 3, brand colors, dark/light modes | 5 hrs. | Rex Bernard G. Gabor | PFPH-8
PFPH-10 | Git repo setup, branching strategy, README.md | 4 hrs. | Tom Kyle B. Caballegan, Mark Leannie Gacutno, Rex Bernard G. Gabor | None
PFPH-11 | Android manifest: runtime permissions (storage, camera) | 3 hrs. | Tom Kyle B. Caballegan | PFPH-1
PFPH-12 | Sprint 1 internal demo + full retrospective | 3 hrs. | Tom Kyle B. Caballegan, Mark Leannie Gacutno, Rex Bernard G. Gabor | PFPH-1 to PFPH-11
PFPH-13 | BUFFER — 10% | 9.6 hrs. | Tom Kyle B. Caballegan, Mark Leannie Gacutno, Rex Bernard G. Gabor | Sprint 1 in done
Sprint 2: Authentication + Dashboard
PFPH-14 | UserModel: fromMap(), toMap(), copyWith() | 3 hrs. | Mark Leannie Gacutno | Sprint 1 complete
PFPH-15 | AuthService: register(), login(), logout(), getCurrentUser() | 8 hrs. | Mark Leannie Gacutno | PFPH-14
PFPH-16 | Login screen UI (email, password, form validation) | 5 hrs. | Rex Bernard G. Gabor | PFPH-15
PFPH-17 | Register screen UI (name, email, password, confirm) | 5 hrs. | Rex Bernard G. Gabor | PFPH-15
PFPH-18 | Forgot password screen (security question local reset) | 4 hrs. | Tom Kyle B. Caballegan | PFPH-15
PFPH-19 | AuthProvider (ChangeNotifier): authState, currentUser, errorMessage | 5 hrs. | Tom Kyle B. Caballegan | PFPH-14, PFPH-15, PFPH-16, PFPH-17
PFPH-20 | Student Dashboard: greeting, stats, recent entries, quick-add FAB | 8 hrs. | Rex Bernard G. Gabor | PFPH-15, PFPH-19
PFPH-21 | Profile setup screen: avatar (image_picker), bio, school, course | 6 hrs. | Tom Kyle B. Caballegan | PFPH-16
PFPH-22 | ProfileService: getProfile(), updateProfile() | 5 hrs. | Mark Leannie Gacutno | PFPH-14, PFPH-21
PFPH-23 | Session persistence: auto-login from SharedPreferences | 4 hrs. | Tom Kyle B. Caballegan | PFPH-15
PFPH-24 | Unit tests: AuthService register/login/logout | 4 hrs. | Mark Leannie Gacutno | PFPH-15
PFPH-25 | Sprint 2 demo + retrospective | 3 hrs. | Tom Kyle B. Caballegan, Mark Leannie Gacutno, Rex Bernard G. Gabor | PFPH-14 to PFPH-24
PFPH-26 | BUFFER — 10% | 9.6 hrs. | Tom Kyle B. Caballegan, Mark Leannie Gacutno, Rex Bernard G. Gabor | Sprint 2 in progress
Sprint 3: Portfolio CRUD I — Projects & Achievements
PFPH-27 | ProjectModel: id, userId, title, desc, techStack, dates, tags | 3 hrs. | Mark Leannie Gacutno | Sprint 2 complete
PFPH-28 | ProjectService: create, getAll, getById, update, delete, search | 8 hrs. | Mark Leannie Gacutno | PFPH-27
PFPH-29 | ProjectsListScreen: ListView.builder + search bar + filter chips | 7 hrs. | Rex Bernard G. Gabor | PFPH-28
PFPH-30 | AddEditProjectScreen: title, desc, tags, dates, tech stack, images | 8 hrs. | Rex Bernard G. Gabor | PFPH-28, PFPH-31
PFPH-31 | ImageStorageService: saveImage(), deleteImage(), compressImage() | 7 hrs. | Tom Kyle B. Caballegan | Sprint 1 complete
PFPH-32 | ProjectDetailScreen: full view + image carousel + edit/delete | 6 hrs. | Tom Kyle B. Caballegan | PFPH-28, PFPH-31
PFPH-33 | AchievementModel: id, userId, title, desc, date, type, imagePath | 2 hrs. | Mark Leannie Gacutno | Sprint 2 complete
PFPH-34 | AchievementService: full CRUD + searchByTitle() | 5 hrs. | Mark Leannie Gacutno | PFPH-33
PFPH-35 | AchievementsListScreen + AddEditAchievementScreen | 6 hrs. | Rex Bernard G. Gabor | PFPH-34
PFPH-36 | ProjectProvider + AchievementProvider (ChangeNotifier) | 5 hrs. | Tom Kyle B. Caballegan | PFPH-28, PFPH-34
PFPH-37 | Reusable widgets: PortfolioCard, EmptyStateWidget, LoadingWidget, TagChip | 4 hrs. | Tom Kyle B. Caballegan | PFPH-29, PFPH-35
PFPH-38 | Sprint 3 demo + retrospective | 3 hrs. | Tom Kyle B. Caballegan, Mark Leannie Gacutno, Rex Bernard G. Gabor | PFPH-27 to PFPH-37
PFPH-39 | BUFFER — 10% | 9.6 hrs. | Tom Kyle B. Caballegan, Mark Leannie Gacutno, Rex Bernard G. Gabor | Sprint 3 in progress
Sprint 4: Portfolio CRUD II — Certificates, Reflections & Skills
PFPH-40 | CertificateModel: id, userId, title, issuer, dates, filePath, type | 3 hrs. | Mark Leannie Gacutno | Sprint 3 complete
PFPH-41 | CertificateService: full CRUD + filterByType() + search | 6 hrs. | Mark Leannie Gacutno | PFPH-40
PFPH-42 | CertificatesListScreen + AddEditCertificateScreen | 7 hrs. | Rex Bernard G. Gabor | PFPH-41
PFPH-43 | Document upload for certificates (image_picker + file_picker) | 5 hrs. | Tom Kyle B. Caballegan | PFPH-11
PFPH-44 | ReflectionModel: id, userId, title, body, mood, tags, isPrivate, date | 2 hrs. | Mark Leannie Gacutno | Sprint 2 complete
PFPH-45 | ReflectionService: full CRUD + searchByBody() (SQLite LIKE or FTS5) | 5 hrs. | Mark Leannie Gacutno | PFPH-44
PFPH-46 | ReflectionsListScreen + ReflectionEditorScreen | 7 hrs. | Rex Bernard G. Gabor | PFPH-45
PFPH-47 | SkillModel: id, userId, name, category, rating 1-5, lastUsed | 3 hrs. | Tom Kyle B. Caballegan | Sprint 2 complete
PFPH-48 | SkillService: full CRUD + sortByRating() + suggestSkillNames() | 4 hrs. | Tom Kyle B. Caballegan | PFPH-47
PFPH-49 | SkillsTrackerScreen: categorized list + rating stars + add/edit modal | 7 hrs. | Tom Kyle B. Caballegan | PFPH-48
PFPH-50 | CertificateProvider + ReflectionProvider + SkillProvider | 5 hrs. | Tom Kyle B. Caballegan | PFPH-41, PFPH-45, PFPH-48
PFPH-51 | PortfolioOverview tab: aggregate all 4 modules with counts + recent | 7 hrs. | Rex Bernard G. Gabor | PFPH-42, PFPH-46, PFPH-49
PFPH-52 | Sprint 4 demo + retrospective | 3 hrs. | Tom Kyle B. Caballegan, Mark Leannie Gacutno, Rex Bernard G. Gabor | PFPH-40 to PFPH-51
PFPH-53 | BUFFER — 10% | 9.6 hrs. | Tom Kyle B. Caballegan, Mark Leannie Gacutno, Rex Bernard G. Gabor | Sprint 4 in progress
Sprint 5: Resume / CV Builder
PFPH-54 | ResumeModel: id, userId, templateId, customSections JSON, isDefault | 3 hrs. | Mark Leannie Gacutno | Sprint 4 complete
PFPH-55 | Design 3 PH resume templates (paper/Figma before coding) | 4 hrs. | Tom Kyle B. Caballegan, Mark Leannie Gacutno, Rex Bernard G. Gabor | Sprint 4 complete
PFPH-56 | ResumeTemplateSimple widget — government/academic style | 8 hrs. | Rex Bernard G. Gabor | PFPH-55
PFPH-57 | ResumeTemplateProfessional widget — corporate PH style | 7 hrs. | Rex Bernard G. Gabor | PFPH-55
PFPH-58 | ResumeTemplateModern widget — fresh grad tech style | 7 hrs. | Tom Kyle B. Caballegan | PFPH-55
PFPH-59 | ResumeDataService: mapPortfolioToResumeData(userId) | 8 hrs. | Mark Leannie Gacutno | Sprint 4 complete
PFPH-60 | TemplateSelectionScreen: 3 template preview cards + select CTA | 5 hrs. | Tom Kyle B. Caballegan | PFPH-56, PFPH-57, PFPH-58
PFPH-61 | ResumeBuilderScreen: live preview + section toggles + field overrides | 8 hrs. | Tom Kyle B. Caballegan, Rex Bernard G. Gabor | PFPH-59, PFPH-60
PFPH-62 | ResumeProvider: selectedTemplate, resumeData, dirtyState | 5 hrs. | Mark Leannie Gacutno | PFPH-59, PFPH-61
PFPH-63 | Photo slot: pick from gallery or use profile photo + 2×2 crop | 4 hrs. | Mark Leannie Gacutno | PFPH-61
PFPH-64 | Unit tests: ResumeDataService field mapping accuracy | 4 hrs. | Tom Kyle B. Caballegan | PFPH-59
PFPH-65 | Sprint 5 demo + retrospective | 3 hrs. | Tom Kyle B. Caballegan, Mark Leannie Gacutno, Rex Bernard G. Gabor | PFPH-54 to PFPH-64
PFPH-66 | BUFFER — 10% | 9.6 hrs. | Tom Kyle B. Caballegan, Mark Leannie Gacutno, Rex Bernard G. Gabor | Sprint 5 in progress
Sprint 6: PDF Export + UI Polish
PFPH-67 | PdfService: generateResumePdf(resumeData, templateId) — pdf package | 10 hrs. | Mark Leannie Gacutno | Sprint 5 complete
PFPH-68 | PDF layout for Template I (Simple) — mirror Flutter widget layout | 7 hrs. | Mark Leannie Gacutno | PFPH-67
PFPH-69 | PDF layout for Template II (Professional) | 7 hrs. | Rex Bernard G. Gabor | PFPH-67
PFPH-70 | PDF layout for Template III (Modern) | 6 hrs. | Rex Bernard G. Gabor | PFPH-67
PFPH-71 | PdfExportScreen: preview (printing pkg) + save to Downloads | 6 hrs. | Tom Kyle B. Caballegan | PFPH-68, PFPH-69, PFPH-70
PFPH-72 | Share PDF via Android share sheet (share_plus) | 3 hrs. | Tom Kyle B. Caballegan | PFPH-71
PFPH-73 | Portfolio PDF export (all entries as structured PDF document) | 6 hrs. | Mark Leannie Gacutno | Sprint 4 complete
PFPH-74 | ExportHistoryService: log exports to audit table | 3 hrs. | Tom Kyle B. Caballegan | PFPH-71
PFPH-75 | UI Polish pass: spacing, loading skeletons, error states all screens | 7 hrs. | Rex Bernard G. Gabor | Sprint 5 complete
PFPH-76 | Micro-animations: page transitions, FAB, card tap feedback | 4 hrs. | Tom Kyle B. Caballegan | PFPH-75
PFPH-77 | Empty state illustrations for all list screens | 4 hrs. | Rex Bernard G. Gabor | PFPH-75
PFPH-78 | Accessibility pass: semantics labels, contrast, font scaling | 3 hrs. | Mark Leannie Gacutno | PFPH-75
PFPH-79 | Sprint 6 demo + retrospective | 3 hrs. | Tom Kyle B. Caballegan, Mark Leannie Gacutno, Rex Bernard G. Gabor | PFPH-67 to PFPH-78
PFPH-80 | BUFFER — 10% | 9.6 hrs. | Tom Kyle B. Caballegan, Mark Leannie Gacutno, Rex Bernard G. Gabor | Sprint 6 in progress
Sprint 7: Admin Panel + Security
PFPH-81 | Admin seeding: setup wizard on first launch (or hardcoded seed admin) | 3 hrs. | Mark Leannie Gacutno | Sprint 6 complete
PFPH-82 | Admin login screen (separate PIN/password + admin badge UI) | 4 hrs. | Rex Bernard G. Gabor | PFPH-81
PFPH-83 | AdminDashboard: total users, portfolios, exports, storage used | 7 hrs. | Rex Bernard G. Gabor | PFPH-81, PFPH-82
PFPH-84 | AdminUserListScreen: all students + portfolio counts + search | 6 hrs. | Tom Kyle B. Caballegan | PFPH-83
PFPH-85 | AdminPortfolioViewScreen: read-only view of any student's portfolio | 5 hrs. | Tom Kyle B. Caballegan | PFPH-84
PFPH-86 | AdminDataManagementScreen: delete user, export all data, wipe DB | 6 hrs. | Mark Leannie Gacutno | PFPH-83
PFPH-87 | BackupService: export full SQLite DB as .db file to Downloads | 5 hrs. | Mark Leannie Gacutno | PFPH-86
PFPH-88 | RestoreService: import .db backup (schema version validation) | 5 hrs. | Mark Leannie Gacutno | PFPH-87
PFPH-89 | App PIN lock screen: 4-digit PIN, auto-lock after 5 min idle | 5 hrs. | Tom Kyle B. Caballegan | Sprint 2 complete
PFPH-90 | BiometricService: optional fingerprint auth (local_auth pkg) | 5 hrs. | Tom Kyle B. Caballegan | PFPH-89
PFPH-91 | Input sanitization audit: review all SQL queries in all services | 4 hrs. | Rex Bernard G. Gabor | Sprint 1 to Sprint 6 services complete
PFPH-92 | Audit log: track login attempts, failed PINs, admin actions | 4 hrs. | Rex Bernard G. Gabor | PFPH-83, PFPH-91
PFPH-93 | Sprint 7 demo + retrospective | 3 hrs. | Tom Kyle B. Caballegan, Mark Leannie Gacutno, Rex Bernard G. Gabor | PFPH-81 to PFPH-92
PFPH-94 | BUFFER — 10% | 9.6 hrs. | Tom Kyle B. Caballegan, Mark Leannie Gacutno, Rex Bernard G. Gabor | Sprint 7 in progress
Sprint 8: QA, Bug Fixes & APK Release
PFPH-95 | Full regression test pass (manual end-to-end all user flows) | 12 hrs. | Tom Kyle B. Caballegan, Mark Leannie Gacutno, Rex Bernard G. Gabor | Sprint 7 complete
PFPH-96 | Unit tests for all Services (target ≥80% service layer coverage) | 8 hrs. | Mark Leannie Gacutno | Sprint 7 complete
PFPH-97 | Widget tests: Login, Dashboard, ResumeBuilderScreen | 6 hrs. | Tom Kyle B. Caballegan | Sprint 7 complete
PFPH-98 | Bug fix sprint: Critical → High → Medium (skip Low) | 10 hrs. | Tom Kyle B. Caballegan, Mark Leannie Gacutno, Rex Bernard G. Gabor | PFPH-95, PFPH-96, PFPH-97
PFPH-99 | Performance profiling: Flutter DevTools (fps, memory, DB query times) | 4 hrs. | Rex Bernard G. Gabor | PFPH-95
PFPH-100 | Fix performance regressions from profiling | 4 hrs. | Tom Kyle B. Caballegan | PFPH-99
PFPH-101 | Final UI pass: typography, spacing, icon sizes — all screens | 5 hrs. | Rex Bernard G. Gabor | PFPH-98, PFPH-100
PFPH-102 | Keystore generation + app signing config | 3 hrs. | Tom Kyle B. Caballegan | Sprint 7 complete
PFPH-103 | flutter build apk --release --split-per-abi | 2 hrs. | Tom Kyle B. Caballegan | PFPH-102
PFPH-104 | Install + test release APK on 2 physical Android devices | 4 hrs. | Tom Kyle B. Caballegan, Rex Bernard G. Gabor | PFPH-103
PFPH-105 | Documentation: README, 1-page user manual, DB schema diagram | 6 hrs. | Mark Leannie Gacutno | Sprint 1 to Sprint 7 complete
PFPH-106 | Capstone presentation slides + demo script + Q&A rehearsal | 6 hrs. | Tom Kyle B. Caballegan, Mark Leannie Gacutno, Rex Bernard G. Gabor | PFPH-95, PFPH-105
PFPH-107 | Final retrospective: lessons learned, what to keep, future roadmap | 3 hrs. | Tom Kyle B. Caballegan, Mark Leannie Gacutno, Rex Bernard G. Gabor | PFPH-95 to PFPH-106
PFPH-108 | BUFFER — 10% | 9.6 hrs. | Tom Kyle B. Caballegan, Mark Leannie Gacutno, Rex Bernard G. Gabor | Sprint 8 in progress
| SPRINT TOTAL | Sprint 1: 63.6 hrs.; Sprint 2: 69.6 hrs.; Sprint 3: 73.6 hrs.; Sprint 4: 73.6 hrs.; Sprint 5: 75.6 hrs.; Sprint 6: 78.6 hrs.; Sprint 7: 71.6 hrs.; Sprint 8: 82.6 hrs. | Tom Kyle B. Caballegan, Mark Leannie Gacutno, Rex Bernard G. Gabor | All sprint tasks complete
| GRAND TOTAL | 588.8 hrs. | Tom Kyle B. Caballegan, Mark Leannie Gacutno, Rex Bernard G. Gabor | Sprint 1-8 complete