## Master Roadmap
Task No. | Description | Duration (hours) | Assignee | Prerequisite
Sprint 1: Foundation & Architecture
PFPH-1 | SQLite schema design — all 10 tables, ERD sign-off | 8 hrs. | Mark Leannie Gacutno | None
PFPH-2 | DatabaseService singleton: open(), close(), getDatabase(), migrations | 6 hrs. | Mark Leannie Gacutno | PFPH-1
PFPH-3 | AppRouter (GoRouter) — define ALL named routes upfront | 5 hrs. | Mark Leannie Gacutno | PFPH-2
PFPH-4 | Git repo setup, branching strategy, README.md (Project Coordination) | 4 hrs. | Tom Kyle B. Caballegan, Mark Leannie Gacutno, Rex Bernard G. Gabor | PFPH-3
PFPH-5 | AppConstants: colors, font sizes, padding, DB name, version | 3 hrs. | Mark Leannie Gacutno | PFPH-4
PFPH-6 | Android manifest: runtime permissions (storage, camera) | 3 hrs. | Mark Leannie Gacutno | PFPH-5
PFPH-7 | Enforce folder structure — create ALL placeholder .dart files | 3 hrs. | Mark Leannie Gacutno | PFPH-6
Sprint 2: Authentication + Dashboard
PFPH-8 | AuthService: register(), login(), logout(), getCurrentUser() | 8 hrs. | Mark Leannie Gacutno | Sprint 1 complete
PFPH-9 | Student Dashboard: greeting, stats, recent entries, quick-add FAB | 8 hrs. | Mark Leannie Gacutno | PFPH-8
PFPH-10 | Session persistence: auto-login from SharedPreferences | 4 hrs. | Mark Leannie Gacutno | PFPH-9
PFPH-11 | UserModel: fromMap(), toMap(), copyWith() | 3 hrs. | Mark Leannie Gacutno | PFPH-10
PFPH-12 | Unit tests: AuthService register/login/logout | 4 hrs. | Mark Leannie Gacutno | PFPH-11
PFPH-13 | ProfileService: getProfile(), updateProfile() | 5 hrs. | Mark Leannie Gacutno | PFPH-12
Sprint 3: Portfolio CRUD I — Projects & Achievements
PFPH-14 | ProjectService: create, getAll, getById, update, delete, search | 8 hrs. | Mark Leannie Gacutno | Sprint 2 complete
PFPH-15 | ProjectsListScreen: ListView.builder + search bar + filter chips | 7 hrs. | Mark Leannie Gacutno | PFPH-14
PFPH-16 | ProjectDetailScreen: full view + image carousel + edit/delete | 6 hrs. | Mark Leannie Gacutno | PFPH-15
PFPH-17 | AchievementsListScreen + AddEditAchievementScreen | 6 hrs. | Mark Leannie Gacutno | PFPH-16
PFPH-18 | ProjectModel: id, userId, title, desc, techStack, dates, tags | 3 hrs. | Mark Leannie Gacutno | PFPH-17
PFPH-19 | AchievementModel: id, userId, title, desc, date, type, imagePath | 2 hrs. | Mark Leannie Gacutno | PFPH-18
Sprint 4: Portfolio CRUD II — Certificates, Reflections & Skills
PFPH-20 | CertificateService: full CRUD + filterByType() + search | 6 hrs. | Mark Leannie Gacutno | Sprint 3 complete
PFPH-21 | CertificatesListScreen + AddEditCertificateScreen | 7 hrs. | Mark Leannie Gacutno | PFPH-20
PFPH-22 | ReflectionsListScreen + ReflectionEditorScreen | 7 hrs. | Mark Leannie Gacutno | PFPH-21
PFPH-23 | Document upload for certificates (image_picker + file_picker) | 5 hrs. | Mark Leannie Gacutno | PFPH-22
PFPH-24 | SkillService: full CRUD + sortByRating() + suggestSkillNames() | 4 hrs. | Mark Leannie Gacutno | PFPH-23
PFPH-25 | CertificateModel: id, userId, title, issuer, dates, filePath, type | 3 hrs. | Mark Leannie Gacutno | PFPH-24
Sprint 5: Resume / CV Builder
PFPH-26 | Design 3 PH resume templates (paper/Figma before coding) (Design Support) | 4 hrs. | Tom Kyle B. Caballegan | Sprint 4 complete
PFPH-27 | ResumeTemplateSimple widget — government/academic style | 8 hrs. | Mark Leannie Gacutno | PFPH-26
PFPH-28 | ResumeDataService: mapPortfolioToResumeData(userId) | 8 hrs. | Mark Leannie Gacutno | PFPH-27
PFPH-29 | TemplateSelectionScreen: 3 template preview cards + select CTA | 5 hrs. | Mark Leannie Gacutno | PFPH-28
PFPH-30 | Photo slot: pick from gallery or use profile photo + 2×2 crop | 4 hrs. | Mark Leannie Gacutno | PFPH-29
PFPH-31 | ResumeModel: id, userId, templateId, customSections JSON, isDefault | 3 hrs. | Mark Leannie Gacutno | PFPH-30
Sprint 6: PDF Export + UI Polish
PFPH-32 | PDF layout for Template I (Simple) — mirror Flutter widget layout | 7 hrs. | Mark Leannie Gacutno | Sprint 5 complete
PFPH-33 | PDF layout for Template II (Professional) | 7 hrs. | Mark Leannie Gacutno | PFPH-32
PFPH-34 | UI Polish pass: spacing, loading skeletons, error states all screens (UI Review Support) | 7 hrs. | Rex Bernard G. Gabor | PFPH-33
PFPH-35 | Micro-animations: page transitions, FAB, card tap feedback | 4 hrs. | Mark Leannie Gacutno | PFPH-34
PFPH-36 | Empty state illustrations for all list screens (Asset Preparation Support) | 4 hrs. | Tom Kyle B. Caballegan | PFPH-35
PFPH-37 | Accessibility pass: semantics labels, contrast, font scaling (Accessibility QA Support) | 3 hrs. | Rex Bernard G. Gabor | PFPH-36
Sprint 7: Admin Panel + Security
PFPH-38 | Admin login screen (separate PIN/password + admin badge UI) | 4 hrs. | Mark Leannie Gacutno | Sprint 6 complete
PFPH-39 | AdminUserListScreen: all students + portfolio counts + search | 6 hrs. | Mark Leannie Gacutno | PFPH-38
PFPH-40 | AdminDataManagementScreen: delete user, export all data, wipe DB | 6 hrs. | Mark Leannie Gacutno | PFPH-39
PFPH-41 | BackupService: export full SQLite DB as .db file to Downloads | 5 hrs. | Mark Leannie Gacutno | PFPH-40
PFPH-42 | Input sanitization audit: review all SQL queries in all services (Security Review Support) | 4 hrs. | Rex Bernard G. Gabor | PFPH-41
PFPH-43 | Admin seeding: setup wizard on first launch (or hardcoded seed admin) | 3 hrs. | Mark Leannie Gacutno | PFPH-42
PFPH-44 | Audit log: track login attempts, failed PINs, admin actions | 4 hrs. | Mark Leannie Gacutno | PFPH-43
Sprint 8: QA, Bug Fixes & APK Release
PFPH-45 | Full regression test pass (manual end-to-end all user flows) (Manual QA) | 12 hrs. | Tom Kyle B. Caballegan, Mark Leannie Gacutno, Rex Bernard G. Gabor | Sprint 7 complete
PFPH-46 | Unit tests for all Services (target ≥80% service layer coverage) | 8 hrs. | Mark Leannie Gacutno | PFPH-45
PFPH-47 | Widget tests: Login, Dashboard, ResumeBuilderScreen | 6 hrs. | Mark Leannie Gacutno | PFPH-46
PFPH-48 | Fix performance regressions from profiling | 4 hrs. | Mark Leannie Gacutno | PFPH-47
PFPH-49 | flutter build apk --release --split-per-abi | 2 hrs. | Mark Leannie Gacutno | PFPH-48
| SPRINT TOTAL | Sprint 1: 32 hrs.; Sprint 2: 32 hrs.; Sprint 3: 32 hrs.; Sprint 4: 32 hrs.; Sprint 5: 32 hrs.; Sprint 6: 32 hrs.; Sprint 7: 32 hrs.; Sprint 8: 32 hrs. | Mark Leannie Gacutno | 32 hrs each sprint (no demo/retro, no buffer)
| GRAND TOTAL | 256 hrs. | Mark Leannie Gacutno | Single developer delivery plan