## Master Roadmap
Task No. | Description | Duration (hours) | Assignee | Prerequisite
Sprint 1: Foundation & Architecture
PFPH-1 | SQLite schema design — all 10 tables, ERD sign-off (Completed in codebase) (Part 1/2) | 4 hrs. | Mark Leannie Gacutno | None
PFPH-2 | SQLite schema design — all 10 tables, ERD sign-off (Completed in codebase) (Part 2/2) | 4 hrs. | Mark Leannie Gacutno | PFPH-1
PFPH-3 | DatabaseService singleton: open(), close(), getDatabase(), migrations (Completed in codebase) (Part 1/2) | 3 hrs. | Mark Leannie Gacutno | PFPH-2
PFPH-4 | DatabaseService singleton: open(), close(), getDatabase(), migrations (Completed in codebase) (Part 2/2) | 3 hrs. | Mark Leannie Gacutno | PFPH-3
PFPH-5 | AppRouter (GoRouter) — define ALL named routes upfront (Completed in codebase) (Part 1/2) | 2.5 hrs. | Mark Leannie Gacutno | PFPH-4
PFPH-6 | AppRouter (GoRouter) — define ALL named routes upfront (Completed in codebase) (Part 2/2) | 2.5 hrs. | Mark Leannie Gacutno | PFPH-5
PFPH-7 | AppConstants: colors, font sizes, padding, DB name, version (Completed in codebase) | 3 hrs. | Mark Leannie Gacutno | PFPH-6
PFPH-8 | Android manifest: runtime permissions (storage, camera) (Completed in codebase) | 3 hrs. | Mark Leannie Gacutno | PFPH-7
PFPH-9 | Flutter project init, pubspec.yaml, all package setup (Completed in codebase) | 4 hrs. | Mark Leannie Gacutno | PFPH-8
PFPH-10 | Enforce folder structure — create ALL placeholder .dart files (Completed in codebase) | 3 hrs. | Mark Leannie Gacutno | PFPH-9
Sprint 2: Authentication + Dashboard
PFPH-11 | AuthService: register(), login(), logout(), getCurrentUser() (Completed in codebase) (Part 1/2) | 4 hrs. | Mark Leannie Gacutno | Sprint 1 scoped tasks complete
PFPH-12 | AuthService: register(), login(), logout(), getCurrentUser() (Completed in codebase) (Part 2/2) | 4 hrs. | Mark Leannie Gacutno | PFPH-11
PFPH-13 | Student Dashboard: greeting, stats, recent entries, quick-add FAB (Completed in codebase) (Part 1/2) | 4 hrs. | Rex Bernard G. Gabor | PFPH-12
PFPH-14 | Student Dashboard: greeting, stats, recent entries, quick-add FAB (Completed in codebase) (Part 2/2) | 4 hrs. | Rex Bernard G. Gabor | PFPH-13
PFPH-15 | Login screen UI (email, password, form validation) (Completed in codebase) (Part 1/2) | 2.5 hrs. | Rex Bernard G. Gabor | PFPH-14
PFPH-16 | Login screen UI (email, password, form validation) (Completed in codebase) (Part 2/2) | 2.5 hrs. | Rex Bernard G. Gabor | PFPH-15
PFPH-17 | UserModel: fromMap(), toMap(), copyWith() (Completed in codebase) | 3 hrs. | Mark Leannie Gacutno | PFPH-16
PFPH-18 | Session persistence: auto-login from SharedPreferences (Completed in codebase) | 4 hrs. | Mark Leannie Gacutno | PFPH-17
PFPH-19 | Unit tests: AuthService register/login/logout (Completed in codebase) | 4 hrs. | Tom Kyle B. Caballegan, Mark Leannie Gacutno, Rex Bernard G. Gabor | PFPH-18
Sprint 3: Portfolio CRUD I — Projects & Achievements
PFPH-20 | ProjectModel: id, userId, title, desc, techStack, dates, tags (Completed in codebase) | 3 hrs. | Mark Leannie Gacutno | Sprint 2 scoped tasks complete
PFPH-21 | ProjectService: create, getAll, getById, update, delete, search (Completed in codebase) (Part 1/2) | 4 hrs. | Mark Leannie Gacutno | PFPH-20
PFPH-22 | ProjectService: create, getAll, getById, update, delete, search (Completed in codebase) (Part 2/2) | 4 hrs. | Mark Leannie Gacutno | PFPH-21
PFPH-23 | ProjectsListScreen: ListView.builder + search bar + filter chips (Completed in codebase) (Part 1/2) | 3.5 hrs. | Rex Bernard G. Gabor | PFPH-22
PFPH-24 | ProjectsListScreen: ListView.builder + search bar + filter chips (Completed in codebase) (Part 2/2) | 3.5 hrs. | Rex Bernard G. Gabor | PFPH-23
PFPH-25 | AchievementService: full CRUD + searchByTitle() (Completed in codebase) (Part 1/2) | 2.5 hrs. | Mark Leannie Gacutno | PFPH-24
PFPH-26 | AchievementService: full CRUD + searchByTitle() (Completed in codebase) (Part 2/2) | 2.5 hrs. | Mark Leannie Gacutno | PFPH-25
PFPH-27 | ProjectProvider + AchievementProvider (ChangeNotifier) (Completed in codebase) (Part 1/2) | 2.5 hrs. | Mark Leannie Gacutno | PFPH-26
PFPH-28 | ProjectProvider + AchievementProvider (ChangeNotifier) (Completed in codebase) (Part 2/2) | 2.5 hrs. | Mark Leannie Gacutno | PFPH-27
PFPH-29 | Reusable widgets: PortfolioCard, EmptyStateWidget, LoadingWidget, TagChip (Completed in codebase) | 4 hrs. | Mark Leannie Gacutno | PFPH-28
Sprint 4: Portfolio CRUD II — Certificates, Reflections & Skills
PFPH-30 | CertificateModel: id, userId, title, issuer, dates, filePath, type (Completed in codebase) | 3 hrs. | Mark Leannie Gacutno | Sprint 3 scoped tasks complete
PFPH-31 | CertificateService: full CRUD + filterByType() + search (Completed in codebase) (Part 1/2) | 3 hrs. | Mark Leannie Gacutno | PFPH-30
PFPH-32 | CertificateService: full CRUD + filterByType() + search (Completed in codebase) (Part 2/2) | 3 hrs. | Mark Leannie Gacutno | PFPH-31
PFPH-33 | CertificatesListScreen + AddEditCertificateScreen (Completed in codebase) (Part 1/2) | 3.5 hrs. | Rex Bernard G. Gabor | PFPH-32
PFPH-34 | CertificatesListScreen + AddEditCertificateScreen (Completed in codebase) (Part 2/2) | 3.5 hrs. | Rex Bernard G. Gabor | PFPH-33
PFPH-35 | ReflectionsListScreen + ReflectionEditorScreen (Completed in codebase) (Part 1/2) | 3.5 hrs. | Rex Bernard G. Gabor | PFPH-34
PFPH-36 | ReflectionsListScreen + ReflectionEditorScreen (Completed in codebase) (Part 2/2) | 3.5 hrs. | Rex Bernard G. Gabor | PFPH-35
PFPH-37 | SkillModel: id, userId, name, category, rating 1-5, lastUsed (Completed in codebase) | 3 hrs. | Mark Leannie Gacutno | PFPH-36
PFPH-38 | SkillService: full CRUD + sortByRating() + suggestSkillNames() (Completed in codebase) | 4 hrs. | Mark Leannie Gacutno | PFPH-37
PFPH-39 | ReflectionModel: id, userId, title, body, mood, tags, isPrivate, date (Completed in codebase) | 2 hrs. | Mark Leannie Gacutno | PFPH-38
Sprint 5: Resume / CV Builder
PFPH-40 | ResumeModel: id, userId, templateId, customSections JSON, isDefault | 3 hrs. | Rex Bernard G. Gabor | Sprint 4 scoped tasks complete
PFPH-41 | Design 3 PH resume templates (paper/Figma before coding) | 4 hrs. | Rex Bernard G. Gabor | PFPH-40
PFPH-42 | ResumeTemplateSimple widget — government/academic style (Part 1/2) | 4 hrs. | Rex Bernard G. Gabor | PFPH-41
PFPH-43 | ResumeTemplateSimple widget — government/academic style (Part 2/2) | 4 hrs. | Rex Bernard G. Gabor | PFPH-42
PFPH-44 | ResumeDataService: mapPortfolioToResumeData(userId) (Part 1/2) | 4 hrs. | Mark Leannie Gacutno | PFPH-43
PFPH-45 | ResumeDataService: mapPortfolioToResumeData(userId) (Part 2/2) | 4 hrs. | Mark Leannie Gacutno | PFPH-44
PFPH-46 | TemplateSelectionScreen: 3 template preview cards + select CTA (Part 1/2) | 2.5 hrs. | Rex Bernard G. Gabor | PFPH-45
PFPH-47 | TemplateSelectionScreen: 3 template preview cards + select CTA (Part 2/2) | 2.5 hrs. | Rex Bernard G. Gabor | PFPH-46
PFPH-48 | Photo slot: pick from gallery or use profile photo + 2×2 crop | 4 hrs. | Mark Leannie Gacutno | PFPH-47
Sprint 6: PDF Export + UI Polish
PFPH-49 | PdfService: generateResumePdf(resumeData, templateId) — pdf package (Part 1/3) | 3.3 hrs. | Rex Bernard G. Gabor | Sprint 5 scoped tasks complete
PFPH-50 | PdfService: generateResumePdf(resumeData, templateId) — pdf package (Part 2/3) | 3.3 hrs. | Rex Bernard G. Gabor | PFPH-49
PFPH-51 | PdfService: generateResumePdf(resumeData, templateId) — pdf package (Part 3/3) | 3.4 hrs. | Rex Bernard G. Gabor | PFPH-50
PFPH-52 | PdfExportScreen: preview (printing pkg) + save to Downloads (Part 1/2) | 3 hrs. | Rex Bernard G. Gabor | PFPH-51
PFPH-53 | PdfExportScreen: preview (printing pkg) + save to Downloads (Part 2/2) | 3 hrs. | Rex Bernard G. Gabor | PFPH-52
PFPH-54 | Portfolio PDF export (all entries as structured PDF document) (Part 1/2) | 3 hrs. | Mark Leannie Gacutno | PFPH-53
PFPH-55 | Portfolio PDF export (all entries as structured PDF document) (Part 2/2) | 3 hrs. | Mark Leannie Gacutno | PFPH-54
PFPH-56 | UI Polish pass: spacing, loading skeletons, error states all screens (Part 1/2) | 3.5 hrs. | Rex Bernard G. Gabor | PFPH-55
PFPH-57 | UI Polish pass: spacing, loading skeletons, error states all screens (Part 2/2) | 3.5 hrs. | Rex Bernard G. Gabor | PFPH-56
PFPH-58 | Share PDF via Android share sheet (share_plus) | 3 hrs. | Mark Leannie Gacutno | PFPH-57
Sprint 7: Admin Panel + Security
PFPH-59 | AdminDashboard: total users, portfolios, exports, storage used (Part 1/2) | 3.5 hrs. | Rex Bernard G. Gabor | Sprint 6 scoped tasks complete
PFPH-60 | AdminDashboard: total users, portfolios, exports, storage used (Part 2/2) | 3.5 hrs. | Rex Bernard G. Gabor | PFPH-59
PFPH-61 | AdminUserListScreen: all students + portfolio counts + search (Part 1/2) | 3 hrs. | Rex Bernard G. Gabor | PFPH-60
PFPH-62 | AdminUserListScreen: all students + portfolio counts + search (Part 2/2) | 3 hrs. | Rex Bernard G. Gabor | PFPH-61
PFPH-63 | AdminPortfolioViewScreen: read-only view of any student's portfolio (Part 1/2) | 2.5 hrs. | Rex Bernard G. Gabor | PFPH-62
PFPH-64 | AdminPortfolioViewScreen: read-only view of any student's portfolio (Part 2/2) | 2.5 hrs. | Rex Bernard G. Gabor | PFPH-63
PFPH-65 | AdminDataManagementScreen: delete user, export all data, wipe DB (Part 1/2) | 3 hrs. | Rex Bernard G. Gabor | PFPH-64
PFPH-66 | AdminDataManagementScreen: delete user, export all data, wipe DB (Part 2/2) | 3 hrs. | Rex Bernard G. Gabor | PFPH-65
PFPH-67 | Input sanitization audit: review all SQL queries in all services | 4 hrs. | Tom Kyle B. Caballegan, Mark Leannie Gacutno, Rex Bernard G. Gabor | PFPH-66
PFPH-68 | Audit log: track login attempts, failed PINs, admin actions | 4 hrs. | Mark Leannie Gacutno | PFPH-67
Sprint 8: QA, Bug Fixes & APK Release
PFPH-69 | Full regression test pass (manual end-to-end all user flows) (Part 1/3) | 4 hrs. | Tom Kyle B. Caballegan, Mark Leannie Gacutno, Rex Bernard G. Gabor | Sprint 7 scoped tasks complete
PFPH-70 | Full regression test pass (manual end-to-end all user flows) (Part 2/3) | 4 hrs. | Tom Kyle B. Caballegan, Mark Leannie Gacutno, Rex Bernard G. Gabor | PFPH-69
PFPH-71 | Full regression test pass (manual end-to-end all user flows) (Part 3/3) | 4 hrs. | Tom Kyle B. Caballegan, Mark Leannie Gacutno, Rex Bernard G. Gabor | PFPH-70
PFPH-72 | Unit tests for all Services (target ≥80% service layer coverage) (Part 1/2) | 4 hrs. | Tom Kyle B. Caballegan, Mark Leannie Gacutno, Rex Bernard G. Gabor | PFPH-71
PFPH-73 | Unit tests for all Services (target ≥80% service layer coverage) (Part 2/2) | 4 hrs. | Tom Kyle B. Caballegan, Mark Leannie Gacutno, Rex Bernard G. Gabor | PFPH-72
PFPH-74 | Widget tests: Login, Dashboard, ResumeBuilderScreen (Part 1/2) | 3 hrs. | Rex Bernard G. Gabor | PFPH-73
PFPH-75 | Widget tests: Login, Dashboard, ResumeBuilderScreen (Part 2/2) | 3 hrs. | Rex Bernard G. Gabor | PFPH-74
PFPH-76 | Fix performance regressions from profiling | 4 hrs. | Mark Leannie Gacutno | PFPH-75
PFPH-77 | flutter build apk --release --split-per-abi | 2 hrs. | Tom Kyle B. Caballegan | PFPH-76
| SPRINT TOTAL | Sprint 1: 32 hrs.; Sprint 2: 32 hrs.; Sprint 3: 32 hrs.; Sprint 4: 32 hrs.; Sprint 5: 32 hrs.; Sprint 6: 32 hrs.; Sprint 7: 32 hrs.; Sprint 8: 32 hrs. | Tom Kyle B. Caballegan, Mark Leannie Gacutno, Rex Bernard G. Gabor | Micro-tasked plan (piece-by-piece)
| GRAND TOTAL | 256 hrs. | Tom Kyle B. Caballegan, Mark Leannie Gacutno, Rex Bernard G. Gabor