## 📋 Cover
PortFolioPH
Offline Portfolio Builder for Students
8-Sprint Agile Roadmap · 16 Weeks · 768 Total Hours
Team Members | Tom Kyle B. Caballegan ¦ Mark Leannie Gacutno ¦ Rex Bernard G. Gabor
Course Schedule | MTh 4–5:30 PM · W 3–5 PM → 7.5 hrs/week team time
Constraint | 32 hrs / programmer / week = 96 hrs / week total
Tech Stack | Flutter (Android-only) · SQLite · pdf package · image_picker
Duration | 8 Sprints × 2 Weeks = 16 Weeks
Deliverable | Signed Release APK + Capstone Presentation
WORKBOOK SHEETS
📋 Cover | This page — project summary & navigation
📊 Dashboard | Sprint summary, hours budget, milestones
🏃 Sprint 1 | Foundation & architecture
🏃 Sprint 2 | Auth + Dashboard UI
🏃 Sprint 3 | Portfolio CRUD I (Projects, Achievements)
🏃 Sprint 4 | Portfolio CRUD II (Certs, Reflections, Skills)
🏃 Sprint 5 | Resume / CV Builder
🏃 Sprint 6 | PDF Export + UI Polish
🏃 Sprint 7 | Admin Panel + Security
🏃 Sprint 8 | QA, Bug Fixes, APK Release
🗺 Master Tracker | Single source of truth — all sprints
📅 Class Schedule | MTh/W sessions mapped to sprints
📦 Tech Stack | Package manifest + verification checklist
📐 ERD | SQLite schema with entities & relationships
🗂 Flutter Scaffold | Complete folder/file structure with purpose
✅ Day 1 Checklist | Sprint 1 kickoff checklist — ready to run
📈 Metrics | Success KPIs + progress formulas

## 📊 Dashboard
PortFolioPH — Sprint Dashboard Summary
8 Sprints · 16 Weeks · 768 Total Hours · Android-Only Flutter App
Sprint | Weeks | Theme | Goals | Team Hrs | Buffer 10% | Net Hrs | Demo Milestone | Status
1 | 1–2 | Foundation | Project setup, folder structure, DB schema, navigation scaffold | 96 | 9.6 | 86.4 | Splash screen + nav on emulator | Not Started
2 | 3–4 | Auth + UI Core | Login/Register w/ SQLite, dashboard, theming | 96 | 9.6 | 86.4 | Full auth flow + home dashboard | Not Started
3 | 5–6 | Portfolio CRUD I | Projects & Achievements module + image upload | 96 | 9.6 | 86.4 | Add/edit/delete projects with images | Not Started
4 | 7–8 | Portfolio CRUD II | Certificates, Reflections, Skills tracker | 96 | 9.6 | 86.4 | Full portfolio CRUD + skills page | Not Started
5 | 9–10 | Resume Builder | Philippine resume/CV templates, data population | 96 | 9.6 | 86.4 | Resume preview with live portfolio data | Not Started
6 | 11–12 | PDF Export | PDF generation, export, share; UI polish | 96 | 9.6 | 86.4 | Exportable PDF portfolio + resume | Not Started
7 | 13–14 | Admin + Security | Admin local panel, PIN lock, backup/restore | 96 | 9.6 | 86.4 | Admin dashboard + locked student access | Not Started
8 | 15–16 | Release | QA, bug fixes, performance, signed APK | 96 | 9.6 | 86.4 | Signed APK + capstone demo | Not Started
TOTAL | 8 Sprints · 16 Weeks |  |  | 768 | 76.8 | 691.2 | Android APK Submitted | 16 Wks
STATUS LEGEND: | Not Started | In Progress | Done

## 🏃 Sprint 1
Sprint 1: Foundation & Architecture
Goal: Scaffold the entire project so every team member can code independently by end of week 2.
# | Task | Owner(s) | Est Hrs | Notes | Status
1 | Flutter project init, pubspec.yaml, all package setup | TK | 4 | Flutter 3.x stable; Android-only build config | ⬜ Not Started
2 | Enforce folder structure — create ALL placeholder .dart files | TK | 3 | See Flutter Scaffold sheet; no empty folders | ⬜ Not Started
3 | SQLite schema design — all 10 tables, ERD sign-off | ML | 8 | Finalize on Day 1 before writing any code | ⬜ Not Started
4 | DatabaseService singleton: open(), close(), getDatabase(), migrations | ML | 6 | Abstract all raw SQL; no direct sqflite calls in UI ever | ⬜ Not Started
5 | AppRouter (GoRouter) — define ALL named routes upfront | RB | 5 | Map every screen on day 1; fallback to Navigator 2.0 if >4 hrs | ⬜ Not Started
6 | Bottom navigation scaffold + 5 placeholder tab screens | RB | 6 | Tabs: Home, Portfolio, Resume, Skills, Profile | ⬜ Not Started
7 | Splash screen: logo + loading + session check → redirect | TK | 4 | Check SharedPreferences for userId; redirect accordingly | ⬜ Not Started
8 | AppConstants: colors, font sizes, padding, DB name, version | ML | 3 | Zero magic numbers allowed from Sprint 1 onward | ⬜ Not Started
9 | AppTheme: Material 3, brand colors, dark/light modes | RB | 5 | ThemeData centrally defined; never hardcode colors in widgets | ⬜ Not Started
10 | Git repo setup, branching strategy, README.md | TK+ML+RB | 4 | main/develop/feature/* branches; PRs required to merge to develop | ⬜ Not Started
11 | Android manifest: runtime permissions (storage, camera) | TK | 3 | Use permission_handler; request at runtime not install time | ⬜ Not Started
12 | Sprint 1 internal demo + full retrospective | TK+ML+RB | 3 | Run on physical Android device; record screen for evidence | ⬜ Not Started
BUFFER — 10% |  | All | 9.6 | Use only when blocked; do NOT pre-assign tasks here | —
SPRINT TOTAL |  | TK + ML + RB | 59.6 | Target: 96 hrs ¦ Per person: 32 hrs each
⏱ Per-person target: TK = 32 hrs ¦ ML = 32 hrs ¦ RB = 32 hrs (adjust with buffer to balance)
⚠ SPRINT RISK REGISTER
Risk | Likelihood | Impact | Mitigation
SQLite schema changes mid-sprint | Medium | High | Finalize & sign-off ERD on Day 1 before any coding
Team member environment setup issues | High | Low | Block first 2 hrs for collective setup session
GoRouter learning curve | Low | Medium | Fallback to standard Navigator 2.0 if GoRouter takes >4 hrs

## 🏃 Sprint 2
Sprint 2: Authentication + Dashboard
Goal: Students can register, log in, and land on a personalized dashboard. Admins have a separate local entry.
# | Task | Owner(s) | Est Hrs | Notes | Status
1 | UserModel: fromMap(), toMap(), copyWith() | ML | 3 | Immutable; role field: 'student' ¦ 'admin' | ⬜ Not Started
2 | AuthService: register(), login(), logout(), getCurrentUser() | ML | 8 | SHA-256 password hash via crypto pkg; validate all inputs | ⬜ Not Started
3 | Login screen UI (email, password, form validation) | RB | 5 | Show/hide password; disable button while loading | ⬜ Not Started
4 | Register screen UI (name, email, password, confirm) | RB | 5 | Real-time validation; duplicate email check against SQLite | ⬜ Not Started
5 | Forgot password screen (security question local reset) | TK | 4 | Store security question + hashed answer in users table | ⬜ Not Started
6 | AuthProvider (ChangeNotifier): authState, currentUser, errorMessage | TK | 5 | Wrap app in MultiProvider; redirect based on role | ⬜ Not Started
7 | Student Dashboard: greeting, stats, recent entries, quick-add FAB | RB | 8 | FutureBuilder for counts; pull-to-refresh | ⬜ Not Started
8 | Profile setup screen: avatar (image_picker), bio, school, course | TK | 6 | Store avatar as local path; display with Image.file() + errorBuilder | ⬜ Not Started
9 | ProfileService: getProfile(), updateProfile() | ML | 5 | Separate from AuthService (SRP) | ⬜ Not Started
10 | Session persistence: auto-login from SharedPreferences | TK | 4 | On launch, check userId in SharedPreferences → skip login | ⬜ Not Started
11 | Unit tests: AuthService register/login/logout | ML | 4 | flutter_test + in-memory SQLite; cover happy + error paths | ⬜ Not Started
12 | Sprint 2 demo + retrospective | TK+ML+RB | 3 | Demo: register → login → dashboard with name → logout | ⬜ Not Started
BUFFER — 10% |  | All | 9.6 | Use only when blocked; do NOT pre-assign tasks here | —
SPRINT TOTAL |  | TK + ML + RB | 66.6 | Target: 96 hrs ¦ Per person: 32 hrs each
⏱ Per-person target: TK = 32 hrs ¦ ML = 32 hrs ¦ RB = 32 hrs (adjust with buffer to balance)
⚠ SPRINT RISK REGISTER
Risk | Likelihood | Impact | Mitigation
crypto package compatibility on Android API 21 | Low | Medium | Test SHA-256 on API 21 emulator in first coding session
Profile image_picker crash on older Android | Medium | Medium | Wrap in try-catch; fallback to default avatar asset
SharedPreferences vs SQLite session debate | Low | Low | Decision locked: SharedPreferences for session, SQLite for data

## 🏃 Sprint 3
Sprint 3: Portfolio CRUD I — Projects & Achievements
Goal: Students can fully manage Projects and Achievements with rich text and multi-image upload.
# | Task | Owner(s) | Est Hrs | Notes | Status
1 | ProjectModel: id, userId, title, desc, techStack, dates, tags | ML | 3 | imageUrls stored as comma-separated local paths string | ⬜ Not Started
2 | ProjectService: create, getAll, getById, update, delete, search | ML | 8 | All queries WHERE user_id=?; parameterized only, no string concat | ⬜ Not Started
3 | ProjectsListScreen: ListView.builder + search bar + filter chips | RB | 7 | Pagination: LIMIT/OFFSET from first implementation (scalability) | ⬜ Not Started
4 | AddEditProjectScreen: title, desc, tags, dates, tech stack, images | RB | 8 | Same screen for add/edit; null projectId = add mode | ⬜ Not Started
5 | ImageStorageService: saveImage(), deleteImage(), compressImage() | TK | 7 | flutter_image_compress; max 500KB; max 5 images per project | ⬜ Not Started
6 | ProjectDetailScreen: full view + image carousel + edit/delete | TK | 6 | ImageCarousel extracted as reusable widget | ⬜ Not Started
7 | AchievementModel: id, userId, title, desc, date, type, imagePath | ML | 2 | type: Academic ¦ Extracurricular ¦ Competition ¦ Other | ⬜ Not Started
8 | AchievementService: full CRUD + searchByTitle() | ML | 5 | Mirror ProjectService pattern for consistency | ⬜ Not Started
9 | AchievementsListScreen + AddEditAchievementScreen | RB | 6 | Reuse PortfolioCard widget; tag with achievement type chip | ⬜ Not Started
10 | ProjectProvider + AchievementProvider (ChangeNotifier) | TK | 5 | Expose loading/error states; refresh list after every CRUD op | ⬜ Not Started
11 | Reusable widgets: PortfolioCard, EmptyStateWidget, LoadingWidget, TagChip | TK | 4 | Parameterize via constructor; zero hardcoded strings in widgets | ⬜ Not Started
12 | Sprint 3 demo + retrospective | TK+ML+RB | 3 | Demo: add project with 3 images → view → edit → delete | ⬜ Not Started
BUFFER — 10% |  | All | 9.6 | Use only when blocked; do NOT pre-assign tasks here | —
SPRINT TOTAL |  | TK + ML + RB | 70.6 | Target: 96 hrs ¦ Per person: 32 hrs each
⏱ Per-person target: TK = 32 hrs ¦ ML = 32 hrs ¦ RB = 32 hrs (adjust with buffer to balance)
⚠ SPRINT RISK REGISTER
Risk | Likelihood | Impact | Mitigation
Local storage fills with uncompressed images | High | High | Enforce max 500KB via flutter_image_compress before saving
Slow list rendering with 50+ entries | Medium | Medium | Add LIMIT/OFFSET pagination from day 1; never fetchAll()
File path breaks after app reinstall | Medium | High | Store relative paths; resolve absolute path at runtime via getApplicationDocumentsDirectory()

## 🏃 Sprint 4
Sprint 4: Portfolio CRUD II — Certificates, Reflections & Skills
Goal: Students can log certificates, write reflections, and track skills. Full portfolio is complete.
# | Task | Owner(s) | Est Hrs | Notes | Status
1 | CertificateModel: id, userId, title, issuer, dates, filePath, type | ML | 3 | type: Online ¦ Physical ¦ Award; filePath = image or scanned doc | ⬜ Not Started
2 | CertificateService: full CRUD + filterByType() + search | ML | 6 | Support: All / Online / Physical / Award filter tabs | ⬜ Not Started
3 | CertificatesListScreen + AddEditCertificateScreen | RB | 7 | Certificate card shows issuer + expiry badge | ⬜ Not Started
4 | Document upload for certificates (image_picker + file_picker) | TK | 5 | Allow JPG, PNG capture; graceful error if file too large | ⬜ Not Started
5 | ReflectionModel: id, userId, title, body, mood, tags, isPrivate, date | ML | 2 | isPrivate=1 → hidden from PDF exports | ⬜ Not Started
6 | ReflectionService: full CRUD + searchByBody() (SQLite LIKE or FTS5) | ML | 5 | Fallback to LIKE '%query%' if FTS5 unavailable on device | ⬜ Not Started
7 | ReflectionsListScreen + ReflectionEditorScreen | RB | 7 | Editor: title + multiline body + mood picker + tags + private toggle | ⬜ Not Started
8 | SkillModel: id, userId, name, category, rating 1-5, lastUsed | TK | 3 | category: Technical ¦ Soft Skill ¦ Language ¦ Tool | ⬜ Not Started
9 | SkillService: full CRUD + sortByRating() + suggestSkillNames() | TK | 4 | Preset skill list in AppConstants for autocomplete | ⬜ Not Started
10 | SkillsTrackerScreen: categorized list + rating stars + add/edit modal | TK | 7 | AnimatedContainer progress bars per skill rating (1–5) | ⬜ Not Started
11 | CertificateProvider + ReflectionProvider + SkillProvider | TK | 5 | Consistent provider pattern; expose filteredList getter in each | ⬜ Not Started
12 | PortfolioOverview tab: aggregate all 4 modules with counts + recent | RB | 7 | Show: X projects, Y certs, Z reflections, W skills + recent 3 each | ⬜ Not Started
13 | Sprint 4 demo + retrospective | TK+ML+RB | 3 | Demo: full portfolio tour — all 4 modules with real data | ⬜ Not Started
BUFFER — 10% |  | All | 9.6 | Use only when blocked; do NOT pre-assign tasks here | —
SPRINT TOTAL |  | TK + ML + RB | 70.6 | Target: 96 hrs ¦ Per person: 32 hrs each
⏱ Per-person target: TK = 32 hrs ¦ ML = 32 hrs ¦ RB = 32 hrs (adjust with buffer to balance)
⚠ SPRINT RISK REGISTER
Risk | Likelihood | Impact | Mitigation
SQLite FTS5 unavailable on some Android versions | Medium | Medium | Fallback to LIKE '%query%' search — implement from start
ReflectionEditor scope creep (demanding rich text) | High | Medium | Hard limit: plaintext only this sprint. Rich text = backlog.
SkillsTracker UX complexity | Low | Low | Keep simple: name + rating + category. Iterate in Sprint 8.

## 🏃 Sprint 5
Sprint 5: Resume / CV Builder
Goal: Students generate a Philippine-format resume auto-populated with their own portfolio data.
# | Task | Owner(s) | Est Hrs | Notes | Status
1 | ResumeModel: id, userId, templateId, customSections JSON, isDefault | ML | 3 | Persist draft to SQLite so users can return and continue | ⬜ Not Started
2 | Design 3 PH resume templates (paper/Figma before coding) | TK+ML+RB | 4 | Match PH hiring norms: 2×2 photo, personal details on top, objective | ⬜ Not Started
3 | ResumeTemplateSimple widget — government/academic style | RB | 8 | Sections: Personal Info, Objective, Education, Skills, Projects | ⬜ Not Started
4 | ResumeTemplateProfessional widget — corporate PH style | RB | 7 | Sections: Header, Summary, Projects/Experience, Certs, Skills, References | ⬜ Not Started
5 | ResumeTemplateModern widget — fresh grad tech style | TK | 7 | Two-column layout; skills as chips; accent color from AppTheme | ⬜ Not Started
6 | ResumeDataService: mapPortfolioToResumeData(userId) | ML | 8 | User selects which portfolio entries to include per section | ⬜ Not Started
7 | TemplateSelectionScreen: 3 template preview cards + select CTA | TK | 5 | Thumbnail preview; 'Use this template' button per card | ⬜ Not Started
8 | ResumeBuilderScreen: live preview + section toggles + field overrides | TK+RB | 8 | User show/hide sections; edit summary inline; real-time re-render | ⬜ Not Started
9 | ResumeProvider: selectedTemplate, resumeData, dirtyState | ML | 5 | Auto-save draft on every change; restore on screen return | ⬜ Not Started
10 | Photo slot: pick from gallery or use profile photo + 2×2 crop | ML | 4 | image_cropper for 2×2 ratio; make crop optional (not all resumes need photo) | ⬜ Not Started
11 | Unit tests: ResumeDataService field mapping accuracy | TK | 4 | Verify all portfolio fields map correctly to resume fields | ⬜ Not Started
12 | Sprint 5 demo + retrospective | TK+ML+RB | 3 | Demo: select template → auto-fill from portfolio → live preview | ⬜ Not Started
BUFFER — 10% |  | All | 9.6 | Use only when blocked; do NOT pre-assign tasks here | —
SPRINT TOTAL |  | TK + ML + RB | 72.6 | Target: 96 hrs ¦ Per person: 32 hrs each
⏱ Per-person target: TK = 32 hrs ¦ ML = 32 hrs ¦ RB = 32 hrs (adjust with buffer to balance)
⚠ SPRINT RISK REGISTER
Risk | Likelihood | Impact | Mitigation
Resume layout breaks on different screen sizes | High | Medium | Use LayoutBuilder + constraints; test on 4.7" 5.5" 6.5" screens
image_cropper not working on low-end Android | Medium | Medium | Make cropping optional; uncropped fallback always available
Section ordering complexity | Medium | Low | Fixed order in Sprint 5. Drag-to-reorder goes to backlog.

## 🏃 Sprint 6
Sprint 6: PDF Export + UI Polish
Goal: Every resume and portfolio is exportable as a formatted PDF. App UI feels polished and professional.
# | Task | Owner(s) | Est Hrs | Notes | Status
1 | PdfService: generateResumePdf(resumeData, templateId) — pdf package | ML | 10 | Register TTF font (Roboto/Nunito) FIRST to handle Filipino characters | ⬜ Not Started
2 | PDF layout for Template I (Simple) — mirror Flutter widget layout | ML | 7 | Use pw.Page, pw.Column, pw.Text with registered fonts | ⬜ Not Started
3 | PDF layout for Template II (Professional) | RB | 7 | Dividers, bold headers, PH resume structure preserved | ⬜ Not Started
4 | PDF layout for Template III (Modern) | RB | 6 | Two-column pw.Row; skill bars as pw.Container width ratio | ⬜ Not Started
5 | PdfExportScreen: preview (printing pkg) + save to Downloads | TK | 6 | path_provider for Downloads path; show file size after save | ⬜ Not Started
6 | Share PDF via Android share sheet (share_plus) | TK | 3 | One tap → share via Drive, Gmail, WhatsApp, etc. | ⬜ Not Started
7 | Portfolio PDF export (all entries as structured PDF document) | ML | 6 | Separate from resume; includes project images embedded | ⬜ Not Started
8 | ExportHistoryService: log exports to audit table | TK | 3 | SQLite export_history table; shown in Profile as 'My Exports' | ⬜ Not Started
9 | UI Polish pass: spacing, loading skeletons, error states all screens | RB | 7 | Shimmer skeleton loaders on every list screen | ⬜ Not Started
10 | Micro-animations: page transitions, FAB, card tap feedback | TK | 4 | AnimatedContainer, Hero widgets; keep subtle and purposeful | ⬜ Not Started
11 | Empty state illustrations for all list screens | RB | 4 | Lottie animation or simple SVG + 'Tap + to add' message | ⬜ Not Started
12 | Accessibility pass: semantics labels, contrast, font scaling | ML | 3 | Critical for capstone panel; demonstrates engineering maturity | ⬜ Not Started
13 | Sprint 6 demo + retrospective | TK+ML+RB | 3 | Demo: portfolio entry → resume → export PDF → open file on device | ⬜ Not Started
BUFFER — 10% |  | All | 9.6 | Use only when blocked; do NOT pre-assign tasks here | —
SPRINT TOTAL |  | TK + ML + RB | 68.6 | Target: 96 hrs ¦ Per person: 32 hrs each
⏱ Per-person target: TK = 32 hrs ¦ ML = 32 hrs ¦ RB = 32 hrs (adjust with buffer to balance)
⚠ SPRINT RISK REGISTER
Risk | Likelihood | Impact | Mitigation
pdf package font issue with Filipino characters (ñ, special chars) | High | High | Register Roboto TTF font in PdfService before building any layout
PDF with images = file size > 10 MB | Medium | Medium | Compress images before embedding; offer 'no images' export option
printing pkg preview blank on some Android versions | Medium | Medium | Test on API 21, 28, 33 in week 11; fallback to open-file intent

## 🏃 Sprint 7
Sprint 7: Admin Panel + Security
Goal: Admin monitors all portfolio data locally. App secured with PIN + optional biometric.
# | Task | Owner(s) | Est Hrs | Notes | Status
1 | Admin seeding: setup wizard on first launch (or hardcoded seed admin) | ML | 3 | role='admin' in users table; setup wizard creates admin on install | ⬜ Not Started
2 | Admin login screen (separate PIN/password + admin badge UI) | RB | 4 | Show 'Admin Mode' banner; different color scheme for admin screens | ⬜ Not Started
3 | AdminDashboard: total users, portfolios, exports, storage used | RB | 7 | Read-only SQLite aggregates; auto-refresh on focus | ⬜ Not Started
4 | AdminUserListScreen: all students + portfolio counts + search | TK | 6 | Tap student → view their portfolio summary (read-only) | ⬜ Not Started
5 | AdminPortfolioViewScreen: read-only view of any student's portfolio | TK | 5 | Reuse existing screens; disable all edit/delete buttons for admin role | ⬜ Not Started
6 | AdminDataManagementScreen: delete user, export all data, wipe DB | ML | 6 | Confirmation dialog on ALL destructive actions; log to audit_log | ⬜ Not Started
7 | BackupService: export full SQLite DB as .db file to Downloads | ML | 5 | For device migration; include schema version in filename | ⬜ Not Started
8 | RestoreService: import .db backup (schema version validation) | ML | 5 | Validate version before import; warn on mismatch; never auto-overwrite | ⬜ Not Started
9 | App PIN lock screen: 4-digit PIN, auto-lock after 5 min idle | TK | 5 | Store hashed PIN in SharedPreferences; 5 attempts → lock 30 min | ⬜ Not Started
10 | BiometricService: optional fingerprint auth (local_auth pkg) | TK | 5 | Graceful fallback to PIN if biometric unavailable; never crash | ⬜ Not Started
11 | Input sanitization audit: review all SQL queries in all services | RB | 4 | Zero string concatenation in SQL; all values via ? placeholders | ⬜ Not Started
12 | Audit log: track login attempts, failed PINs, admin actions | RB | 4 | audit_log table; shown ONLY in admin panel; append-only | ⬜ Not Started
13 | Sprint 7 demo + retrospective | TK+ML+RB | 3 | Demo: admin login → view all students → backup DB → restore | ⬜ Not Started
BUFFER — 10% |  | All | 9.6 | Use only when blocked; do NOT pre-assign tasks here | —
SPRINT TOTAL |  | TK + ML + RB | 68.6 | Target: 96 hrs ¦ Per person: 32 hrs each
⏱ Per-person target: TK = 32 hrs ¦ ML = 32 hrs ¦ RB = 32 hrs (adjust with buffer to balance)
⚠ SPRINT RISK REGISTER
Risk | Likelihood | Impact | Mitigation
local_auth not working on emulator | High | Low | Biometric is optional; PIN always works; skip biometric on emulator
DB restore corrupting live data | Medium | High | Restore to temp path → validate row counts → swap files
Admin panel scope creep (analytics dashboards) | High | Medium | Strictly: aggregate stats + backup/restore only. No charts this sprint.

## 🏃 Sprint 8
Sprint 8: QA, Bug Fixes & APK Release
Goal: Ship a stable, tested, signed Android APK ready for capstone presentation.
# | Task | Owner(s) | Est Hrs | Notes | Status
1 | Full regression test pass (manual end-to-end all user flows) | TK+ML+RB | 12 | Test script: register → add all entry types → export PDF → admin panel | ⬜ Not Started
2 | Unit tests for all Services (target ≥80% service layer coverage) | ML | 8 | mockito + flutter_test; cover happy path + error path per method | ⬜ Not Started
3 | Widget tests: Login, Dashboard, ResumeBuilderScreen | TK | 6 | pumpWidget + navigation test + state change assertions | ⬜ Not Started
4 | Bug fix sprint: Critical → High → Medium (skip Low) | TK+ML+RB | 10 | Triage all issues; document known Low bugs in README 'Known Issues' | ⬜ Not Started
5 | Performance profiling: Flutter DevTools (fps, memory, DB query times) | RB | 4 | Target: 60fps mid-range Android; all DB queries < 50ms | ⬜ Not Started
6 | Fix performance regressions from profiling | TK | 4 | Const widgets, lazy loading, SQL EXPLAIN QUERY PLAN for slow queries | ⬜ Not Started
7 | Final UI pass: typography, spacing, icon sizes — all screens | RB | 5 | Cross-check every screen against AppConstants; zero hardcoded values | ⬜ Not Started
8 | Keystore generation + app signing config | TK | 3 | Store keystore + password in ALL 3 members' Google Drive immediately | ⬜ Not Started
9 | flutter build apk --release --split-per-abi | TK | 2 | Build arm64-v8a, armeabi-v7a; test arm64 APK on physical device first | ⬜ Not Started
10 | Install + test release APK on 2 physical Android devices | TK+RB | 4 | Minimum: Android 8 (API 26) and Android 13 (API 33) | ⬜ Not Started
11 | Documentation: README, 1-page user manual, DB schema diagram | ML | 6 | Panel judges ask about architecture; rehearse answers | ⬜ Not Started
12 | Capstone presentation slides + demo script + Q&A rehearsal | TK+ML+RB | 6 | Each member owns a section: intro / features / technical deep-dive | ⬜ Not Started
13 | Final retrospective: lessons learned, what to keep, future roadmap | TK+ML+RB | 3 | Document for thesis paper and future reference | ⬜ Not Started
BUFFER — 10% |  | All | 9.6 | Use only when blocked; do NOT pre-assign tasks here | —
SPRINT TOTAL |  | TK + ML + RB | 70.6 | Target: 96 hrs ¦ Per person: 32 hrs each
⏱ Per-person target: TK = 32 hrs ¦ ML = 32 hrs ¦ RB = 32 hrs (adjust with buffer to balance)
⚠ SPRINT RISK REGISTER
Risk | Likelihood | Impact | Mitigation
Critical bugs discovered late in regression | High | High | Fix Critical + High only; document Medium/Low as known issues
Release APK > 50 MB | Medium | Medium | Enable R8/ProGuard; use --split-per-abi to reduce per-arch size
Keystore file lost after project completion | High | High | Back up keystore + password to ALL 3 members' personal Google Drive NOW

## 🗺 Master Tracker
PortFolioPH — Master Sprint Tracker
Single Source of Truth · Update after every sprint retrospective
Sprint | Weeks | Budget Hrs | TK Hrs | ML Hrs | RB Hrs | Total Used | Progress % | Risk Level | Next Demo | Notes
1 | 1–2 | 96 | 32 | 32 | 32 | 96 | 100% | Low | Splash + nav scaffold | Establish architecture
2 | 3–4 | 96 | 32 | 32 | 32 | 96 | 100% | Low | Auth flow + Dashboard | Validate DB service
3 | 5–6 | 96 | 32 | 32 | 32 | 96 | 100% | Medium | Projects + Achievements CRUD | First real data entry
4 | 7–8 | 96 | 32 | 32 | 32 | 96 | 100% | Medium | Full portfolio coverage | All 4 modules working
5 | 9–10 | 96 | 32 | 32 | 32 | 96 | 100% | High | Resume preview live | Most complex sprint
6 | 11–12 | 96 | 32 | 32 | 32 | 96 | 100% | High | PDF export working | Feature complete
7 | 13–14 | 96 | 32 | 32 | 32 | 96 | 100% | Medium | Admin + security demo | Pre-release hardening
8 | 15–16 | 96 | 32 | 32 | 32 | 96 | 100% | Low | Final APK + capstone | Release ✔
TOTAL | 16 Wks | 768 | 256 | 256 | 256 | 768 | 100% | → Target: 768 hrs

## 📅 Class Schedule
Class Time Integration Schedule
MTh 4–5:30 PM (3 hrs/session) · W 3–5 PM (2 hrs/session) · 7.5 hrs/week
Week | Day | Time | Activity | Hrs | Sprint | Deliverable
1 | Mon/Thu | 4–5:30 PM | Sprint 1 kickoff, project init, assign tasks | 3 | S1 | Repo + pubspec.yaml live
1 | Wed | 3–5 PM | DB schema design session (all 3 together) | 2 | S1 | Signed-off ERD
2 | Mon/Thu | 4–5:30 PM | Navigation + AppTheme implementation | 3 | S1 | AppRouter + AppTheme pushed
2 | Wed | 3–5 PM | Sprint 1 demo + Sprint 2 planning | 2 | S1→S2 | Sprint 1 complete ✔
3 | Mon/Thu | 4–5:30 PM | AuthService + login/register screens | 3 | S2 | Auth UI running
3 | Wed | 3–5 PM | Dashboard screen + ProfileService | 2 | S2 | Dashboard with mock data
4 | Mon/Thu | 4–5:30 PM | Session persistence + profile setup | 3 | S2 | Auto-login working
4 | Wed | 3–5 PM | Sprint 2 demo + Sprint 3 planning | 2 | S2→S3 | Sprint 2 complete ✔
5 | Mon/Thu | 4–5:30 PM | ProjectModel + ProjectService CRUD | 3 | S3 | Projects DB ops
5 | Wed | 3–5 PM | Multi-image picker + ProjectsListScreen | 2 | S3 | List with real images
6 | Mon/Thu | 4–5:30 PM | AchievementService + AchievementScreen | 3 | S3 | Achievements CRUD done
6 | Wed | 3–5 PM | Sprint 3 demo + Sprint 4 planning | 2 | S3→S4 | Sprint 3 complete ✔
7 | Mon/Thu | 4–5:30 PM | CertificateModel + document upload | 3 | S4 | Certs with file picker
7 | Wed | 3–5 PM | ReflectionEditor + SkillsTracker screen | 2 | S4 | Both screens functional
8 | Mon/Thu | 4–5:30 PM | PortfolioOverview aggregate screen | 3 | S4 | All 4 modules visible
8 | Wed | 3–5 PM | Sprint 4 demo + Sprint 5 planning | 2 | S4→S5 | Sprint 4 complete ✔
9 | Mon/Thu | 4–5:30 PM | Resume template design + widget build | 3 | S5 | Template I rendered
9 | Wed | 3–5 PM | ResumeDataService mapping | 2 | S5 | Portfolio → resume mapped
10 | Mon/Thu | 4–5:30 PM | ResumeBuilderScreen live preview | 3 | S5 | Live resume preview
10 | Wed | 3–5 PM | Sprint 5 demo + Sprint 6 planning | 2 | S5→S6 | Sprint 5 complete ✔
11 | Mon/Thu | 4–5:30 PM | PdfService per template (I & II) | 3 | S6 | PDF I+II generating
11 | Wed | 3–5 PM | PDF Template III + PdfExportScreen | 2 | S6 | All 3 templates export
12 | Mon/Thu | 4–5:30 PM | UI polish pass + skeleton loaders | 3 | S6 | Polished UI
12 | Wed | 3–5 PM | Sprint 6 demo + Sprint 7 planning | 2 | S6→S7 | Sprint 6 complete ✔
13 | Mon/Thu | 4–5:30 PM | Admin login + AdminDashboard screen | 3 | S7 | Admin panel visible
13 | Wed | 3–5 PM | BackupService + RestoreService | 2 | S7 | DB backup working
14 | Mon/Thu | 4–5:30 PM | PIN lock + BiometricService | 3 | S7 | App secured
14 | Wed | 3–5 PM | Sprint 7 demo + Sprint 8 planning | 2 | S7→S8 | Sprint 7 complete ✔
15 | Mon/Thu | 4–5:30 PM | Full regression test pass | 3 | S8 | Test log complete
15 | Wed | 3–5 PM | Bug fix sprint (Critical + High only) | 2 | S8 | 0 critical bugs
16 | Mon/Thu | 4–5:30 PM | APK signing + capstone rehearsal | 3 | S8 | Signed APK ready
16 | Wed | 3–5 PM | 🎓 CAPSTONE PRESENTATION | 2 | Final | APK submitted ✔
⏱ Class time: 7.5 hrs/week × 16 weeks = 120 hrs ¦ Independent work: 768 – 120 = 648 hrs outside class

## 📦 Tech Stack
Technology Dependency Manifest
Verify ALL packages before Sprint 3 to avoid mid-project blockers
Package | Version | Used In | Risk | Verified | Notes
sqflite | ^2.3.0 | All Sprints | Low | [ ] | Core DB; test on Android API 21+
path_provider | ^2.1.0 | All Sprints | Low | [ ] | Required by sqflite for file paths
provider | ^6.1.0 | All Sprints | Low | [ ] | State management (ChangeNotifier)
go_router | ^13.2.0 | Sprint 1+ | Low | [ ] | Named routes; fallback to Navigator 2.0
shared_preferences | ^2.2.2 | Sprint 2+ | Low | [ ] | Session tokens + PIN hash storage
permission_handler | ^11.3.0 | Sprint 1+ | Medium | [ ] | Runtime permissions for storage/camera
image_picker | ^1.0.7 | Sprint 3+ | Medium | [ ] | Camera + gallery; test on API 21–34
file_picker | ^6.1.1 | Sprint 4+ | Medium | [ ] | Certificate doc uploads (JPG, PNG)
image_cropper | ^5.0.1 | Sprint 5+ | Medium | [ ] | 2×2 photo crop for resume photo slot
pdf | ^3.10.8 | Sprint 6 | High | [ ] | Register TTF font EARLY — test Filipino chars
printing | ^5.12.0 | Sprint 6 | High | [ ] | PDF preview; test on API 21, 28, 33
share_plus | ^7.2.1 | Sprint 6+ | Low | [ ] | Android share sheet for PDF
local_auth | ^2.1.8 | Sprint 7 | Medium | [ ] | Biometric optional; always fallback to PIN
shimmer | ^3.0.0 | Sprint 6+ | Low | [ ] | Skeleton loaders on list screens
flutter_image_compress | ^2.0.0 | Sprint 3+ | Medium | [ ] | Enforce max 500KB before saving images
mockito | ^5.4.4 | Sprint 8 | Low | [ ] | Unit test mocking
flutter_test | SDK | Sprint 2, 5, 8 | Low | [ ] | Built-in; no install needed
crypto | ^3.0.3 | Sprint 2+ | Low | [ ] | SHA-256 password hashing (local)
⚠ Add packages to pubspec.yaml in Sprint 1. Run `flutter pub get` and test critical ones (pdf, printing, image_picker) BEFORE Sprint 3.

## 📐 ERD
SQLite Database Schema (ERD)
All tables use INTEGER PRIMARY KEY AUTOINCREMENT · FK enforced at app layer
TABLE: USERS
Stores both students and admins. role column differentiates.
Column | Type | Nullable | Key | References | Notes
id | INTEGER PK | NOT NULL | PK | — | Auto-increment
name | TEXT | NOT NULL |  | — | Full name
email | TEXT | NOT NULL | UNIQUE | — | Login identifier
password_hash | TEXT | NOT NULL |  | — | SHA-256 hashed
role | TEXT | NOT NULL |  | — | 'student' ¦ 'admin'
avatar_path | TEXT | NULL |  | — | Local file path
bio | TEXT | NULL |  | — | Short bio
school | TEXT | NULL |  | — | Institution name
year_level | TEXT | NULL |  | — | e.g. '3rd Year'
course | TEXT | NULL |  | — | e.g. 'BSIT'
pin_hash | TEXT | NULL |  | — | 4-digit PIN (SHA-256)
security_question | TEXT | NULL |  | — | For PIN reset
security_answer_hash | TEXT | NULL |  | — | Hashed answer
created_at | TEXT | NOT NULL |  | — | ISO 8601 timestamp
updated_at | TEXT | NOT NULL |  | — | ISO 8601 timestamp
TABLE: PROJECTS
Student portfolio projects. Multiple images via project_images table.
Column | Type | Nullable | Key | References | Notes
id | INTEGER PK | NOT NULL | PK | —
user_id | INTEGER | NOT NULL | FK | users.id | CASCADE DELETE
title | TEXT | NOT NULL |  | — | Project title
description | TEXT | NULL |  | — | Full description
tech_stack | TEXT | NULL |  | — | Comma-separated
tags | TEXT | NULL |  | — | JSON array string
start_date | TEXT | NULL |  | — | YYYY-MM-DD
end_date | TEXT | NULL |  | — | NULL if ongoing
project_url | TEXT | NULL |  | — | Optional link
created_at | TEXT | NOT NULL |  | —
updated_at | TEXT | NOT NULL |  | —
TABLE: PROJECT_IMAGES
One-to-many images per project (max 5).
Column | Type | Nullable | Key | References | Notes
id | INTEGER PK | NOT NULL | PK | —
project_id | INTEGER | NOT NULL | FK | projects.id | CASCADE DELETE
file_path | TEXT | NOT NULL |  | — | Local absolute path
sort_order | INTEGER | NOT NULL |  | — | Display order 0–4
created_at | TEXT | NOT NULL |  | —
TABLE: ACHIEVEMENTS
Awards, recognitions, academic achievements.
Column | Type | Nullable | Key | References | Notes
id | INTEGER PK | NOT NULL | PK | —
user_id | INTEGER | NOT NULL | FK | users.id | CASCADE DELETE
title | TEXT | NOT NULL |  | —
description | TEXT | NULL |  | —
date_achieved | TEXT | NULL |  | — | YYYY-MM-DD
type | TEXT | NOT NULL |  | — | Academic¦Extracurricular¦Competition¦Other
image_path | TEXT | NULL |  | — | Optional photo
created_at | TEXT | NOT NULL |  | —
TABLE: CERTIFICATES
Digital or physical certificates with optional file attachment.
Column | Type | Nullable | Key | References | Notes
id | INTEGER PK | NOT NULL | PK | —
user_id | INTEGER | NOT NULL | FK | users.id | CASCADE DELETE
title | TEXT | NOT NULL |  | —
issuer | TEXT | NOT NULL |  | — | Issuing organization
issue_date | TEXT | NULL |  | — | YYYY-MM-DD
expiry_date | TEXT | NULL |  | — | NULL if no expiry
file_path | TEXT | NULL |  | — | Image or scanned PDF path
type | TEXT | NOT NULL |  | — | Online¦Physical¦Award
created_at | TEXT | NOT NULL |  | —
TABLE: REFLECTIONS
Personal journal/reflection entries. isPrivate hides from PDF.
Column | Type | Nullable | Key | References | Notes
id | INTEGER PK | NOT NULL | PK | —
user_id | INTEGER | NOT NULL | FK | users.id | CASCADE DELETE
title | TEXT | NOT NULL |  | —
body | TEXT | NOT NULL |  | — | Plaintext content
mood | TEXT | NULL |  | — | Happy¦Motivated¦Challenged¦Neutral
tags | TEXT | NULL |  | — | JSON array string
is_private | INTEGER | NOT NULL |  | — | 0 = public, 1 = private
date | TEXT | NOT NULL |  | — | YYYY-MM-DD
created_at | TEXT | NOT NULL |  | —
updated_at | TEXT | NOT NULL |  | —
TABLE: SKILLS
Student skill inventory with self-rating.
Column | Type | Nullable | Key | References | Notes
id | INTEGER PK | NOT NULL | PK | —
user_id | INTEGER | NOT NULL | FK | users.id | CASCADE DELETE
name | TEXT | NOT NULL |  | — | e.g. 'Flutter', 'SQL'
category | TEXT | NOT NULL |  | — | Technical¦Soft Skill¦Language¦Tool
rating | INTEGER | NOT NULL |  | — | 1–5 scale
last_used | TEXT | NULL |  | — | YYYY-MM-DD
created_at | TEXT | NOT NULL |  | —
TABLE: RESUMES
Saved resume drafts. One student can have multiple saved drafts.
Column | Type | Nullable | Key | References | Notes
id | INTEGER PK | NOT NULL | PK | —
user_id | INTEGER | NOT NULL | FK | users.id | CASCADE DELETE
template_id | INTEGER | NOT NULL |  | — | 1=Simple 2=Pro 3=Modern
custom_sections | TEXT | NULL |  | — | JSON for section config
summary_override | TEXT | NULL |  | — | User-edited summary text
is_default | INTEGER | NOT NULL |  | — | 1 = default draft
generated_at | TEXT | NOT NULL |  | — | Last generated timestamp
TABLE: EXPORT_HISTORY
Log of all PDF exports for audit trail.
Column | Type | Nullable | Key | References | Notes
id | INTEGER PK | NOT NULL | PK | —
user_id | INTEGER | NOT NULL | FK | users.id | CASCADE DELETE
export_type | TEXT | NOT NULL |  | — | resume¦portfolio
template_id | INTEGER | NULL |  | — | 1–3 for resume exports
file_path | TEXT | NOT NULL |  | — | Saved export file path
exported_at | TEXT | NOT NULL |  | — | ISO 8601 timestamp
TABLE: AUDIT_LOG
Admin-only security and action log.
Column | Type | Nullable | Key | References | Notes
id | INTEGER PK | NOT NULL | PK | —
user_id | INTEGER | NULL | FK | users.id | SET NULL on delete
action | TEXT | NOT NULL |  | — | login¦logout¦pin_fail¦admin_*
target | TEXT | NULL |  | — | Affected entity description
timestamp | TEXT | NOT NULL |  | — | ISO 8601
ip_note | TEXT | NULL |  | — | Device model note

## 🗂 Flutter Scaffold
Flutter Project Folder & File Scaffold
Create ALL files in Sprint 1. Placeholder files lock architecture and prevent import chaos.
File Path | Sprint Created | Owner | Purpose / Contents
lib/main.dart | S1 | TK | Entry point ONLY — runApp(PortFolioPHApp()). Zero business logic here.
lib/app.dart | S1 | TK | MaterialApp.router with GoRouter, ThemeData, and top-level providers.
lib/config/app_constants.dart | S1 | ML | ALL magic values: colors (hex), paddings, font sizes, DB name/version, max image count.
lib/config/app_theme.dart | S1 | RB | ThemeData light + dark. Uses values from AppConstants. Never hardcode in widgets.
lib/config/app_router.dart | S1 | RB | GoRouter config with ALL named routes and redirect guards (auth check).
lib/models/user_model.dart | S1 | ML | UserModel: fromMap(), toMap(), copyWith(). Immutable.
lib/models/project_model.dart | S2 | ML | ProjectModel with imageUrls as List<String>.
lib/models/achievement_model.dart | S3 | ML | AchievementModel with type enum.
lib/models/certificate_model.dart | S4 | ML | CertificateModel with filePath for image/doc.
lib/models/reflection_model.dart | S4 | ML | ReflectionModel with isPrivate bool.
lib/models/skill_model.dart | S4 | TK | SkillModel with rating 1–5 and category enum.
lib/models/resume_model.dart | S5 | ML | ResumeModel with templateId and customSections JSON.
lib/models/export_history_model.dart | S6 | ML | ExportHistoryModel for audit log.
lib/services/database_service.dart | S1 | ML | Singleton. open(), close(), getDatabase(). Runs all migrations.
lib/services/auth_service.dart | S2 | ML | register(), login(), logout(), getCurrentUser(). Uses crypto for hashing.
lib/services/profile_service.dart | S2 | ML | getProfile(), updateProfile(). Separate from auth (SRP).
lib/services/project_service.dart | S3 | ML | createProject(), getAllProjects(userId), updateProject(), deleteProject(), searchProjects().
lib/services/image_storage_service.dart | S3 | TK | saveImageToLocal(), deleteImage(), compressImage(). Max 500KB enforced.
lib/services/achievement_service.dart | S3 | ML | Full CRUD mirroring ProjectService pattern.
lib/services/certificate_service.dart | S4 | ML | Full CRUD + filterByType().
lib/services/reflection_service.dart | S4 | ML | Full CRUD + searchByBody() using SQLite LIKE.
lib/services/skill_service.dart | S4 | TK | Full CRUD + sortByRating().
lib/services/resume_data_service.dart | S5 | ML | mapPortfolioToResumeData(userId) — pulls all 4 modules.
lib/services/pdf_service.dart | S6 | ML | generateResumePdf(), generatePortfolioPdf(). One method per template.
lib/services/backup_service.dart | S7 | ML | exportDatabase(), importDatabase() with schema version validation.
lib/services/security_service.dart | S7 | TK | hashPin(), verifyPin(), logAuditEvent(), checkBiometric().
lib/providers/auth_provider.dart | S2 | TK | ChangeNotifier. Exposes authState, currentUser, isLoading, errorMessage.
lib/providers/profile_provider.dart | S2 | TK | Exposes userProfile; calls ProfileService.
lib/providers/project_provider.dart | S3 | TK | Exposes projects list, loading state; refresh after CRUD.
lib/providers/achievement_provider.dart | S3 | TK | Mirror of ProjectProvider pattern.
lib/providers/certificate_provider.dart | S4 | TK | Exposes filteredList getter by type.
lib/providers/reflection_provider.dart | S4 | TK | Exposes searchResults + isPrivate filter.
lib/providers/skill_provider.dart | S4 | TK | Exposes skills sorted by rating.
lib/providers/resume_provider.dart | S5 | ML | Exposes selectedTemplate, resumeData, dirtyState.
lib/screens/splash_screen.dart | S1 | TK | Logo + loading. Checks session → redirect to home or login.
lib/screens/auth/login_screen.dart | S2 | RB | Email + password form. Calls AuthProvider.login().
lib/screens/auth/register_screen.dart | S2 | RB | Full registration form with real-time validation.
lib/screens/auth/forgot_password_screen.dart | S2 | TK | Security question answer → reset local password.
lib/screens/home/dashboard_screen.dart | S2 | RB | Stats overview + recent entries + quick-add FAB.
lib/screens/profile/profile_setup_screen.dart | S2 | TK | Avatar + bio + school + course setup.
lib/screens/portfolio/projects_list_screen.dart | S3 | RB | ListView.builder + search + filter chips.
lib/screens/portfolio/add_edit_project_screen.dart | S3 | RB | Reusable add/edit form; null = add mode.
lib/screens/portfolio/project_detail_screen.dart | S3 | TK | Full project view + image carousel + edit/delete.
lib/screens/portfolio/achievements_screen.dart | S3 | RB | Achievements list + add/edit.
lib/screens/portfolio/certificates_screen.dart | S4 | RB | Certificates list + document upload.
lib/screens/portfolio/reflections_screen.dart | S4 | RB | Reflections list + editor screen.
lib/screens/portfolio/skills_screen.dart | S4 | TK | Skills tracker with animated progress bars.
lib/screens/portfolio/portfolio_overview_screen.dart | S4 | RB | Aggregate view: counts + recent from all 4 modules.
lib/screens/resume/template_selection_screen.dart | S5 | TK | 3 template preview cards.
lib/screens/resume/resume_builder_screen.dart | S5 | TK/RB | Live preview + section toggles + inline edits.
lib/screens/export/pdf_export_screen.dart | S6 | TK | PDF preview (printing pkg) + save to Downloads + share.
lib/screens/admin/admin_login_screen.dart | S7 | RB | Separate admin PIN/password entry.
lib/screens/admin/admin_dashboard_screen.dart | S7 | RB | Aggregate stats read from SQLite.
lib/screens/admin/admin_user_list_screen.dart | S7 | TK | All students + search + portfolio count.
lib/screens/admin/admin_data_screen.dart | S7 | ML | Delete user, wipe DB, export all data.
lib/screens/settings/security_screen.dart | S7 | TK | PIN setup + biometric toggle.
lib/widgets/portfolio_card.dart | S3 | TK | Reusable card for projects, certs, achievements. Parameterized.
lib/widgets/image_carousel.dart | S3 | TK | PageView-based carousel for project images.
lib/widgets/empty_state_widget.dart | S3 | TK | Lottie/SVG + message for empty lists.
lib/widgets/loading_widget.dart | S3 | TK | Centered CircularProgressIndicator with optional message.
lib/widgets/tag_chip.dart | S3 | TK | Colorized chip for tags/categories.
lib/widgets/skill_bar.dart | S4 | TK | AnimatedContainer progress bar for skill rating.
lib/widgets/resume_template_simple.dart | S5 | RB | Flutter widget rendering Simple PH resume layout.
lib/widgets/resume_template_professional.dart | S5 | RB | Flutter widget rendering Professional PH resume.
lib/widgets/resume_template_modern.dart | S5 | TK | Flutter widget rendering Modern two-column resume.
lib/widgets/skeleton_loader.dart | S6 | RB | Shimmer skeleton for list and card loading states.
lib/widgets/confirm_dialog.dart | S7 | RB | Reusable confirmation dialog with destructive action warning.
lib/utils/validators.dart | S2 | ML | validateEmail(), validatePassword(), validateRequired(). Returns String? error.
lib/utils/date_formatter.dart | S2 | ML | formatDate(), parseDate(), toISO8601(). Uses intl package.
lib/utils/file_utils.dart | S3 | TK | getLocalPath(), generateUniqueFilename(), deleteIfExists().
lib/utils/pdf_utils.dart | S6 | ML | registerFonts(), buildPdfHeader(), buildPdfDivider() helpers.
💡 In Sprint 1: create ALL files above as empty placeholders. This locks the architecture and prevents spaghetti imports.

## ✅ Day 1 Checklist
Sprint 1 — Day 1 Kickoff Checklist
Complete ALL items in your first class session (Mon/Thu 4–5:30 PM). Don't leave until rows 1–8 are checked.
✓ | Task | Owner | Time (min) | Definition of Done
[ ] | Install Flutter SDK (stable channel) + Android Studio on ALL 3 laptops | TK+ML+RB | 30 | flutter doctor shows no errors on each machine
[ ] | Create Flutter project: flutter create portfolioph --org com.portfolioph | TK | 5 | Project runs on emulator/device showing default counter app
[ ] | Add ALL packages to pubspec.yaml (see Tech Stack sheet) | TK | 10 | flutter pub get succeeds with 0 errors
[ ] | Delete default counter app code from lib/main.dart | TK | 5 | main.dart has only empty MaterialApp scaffold
[ ] | Create full folder structure (see Flutter Scaffold sheet) | ML | 15 | All folders exist; git status shows them
[ ] | Create app_constants.dart with placeholder values | ML | 15 | File exists with AppConstants class; no empty files
[ ] | Create database_service.dart with open() stub | ML | 20 | DatabaseService singleton compiles without errors
[ ] | Create app_router.dart with 3 placeholder routes | RB | 15 | GoRouter compiles; app navigates between 2 blank screens
[ ] | Create app_theme.dart with brand colors | RB | 15 | ThemeData with primaryColor applied to app
[ ] | Initialize Git repo + push to GitHub/GitLab | TK | 10 | Remote repo visible; all 3 members can clone it
[ ] | Set up branching strategy: main / develop / feature/* | TK | 5 | develop branch exists; push protection on main
[ ] | Create README.md: project name, team, setup instructions | ML | 10 | README renders correctly on GitHub
[ ] | Android manifest: add storage + camera permissions | TK | 10 | permissions listed in AndroidManifest.xml
[ ] | Run app on physical Android device or emulator | TK+ML+RB | 10 | App launches without crashes on Android
[ ] | Take screenshot of running app + push to repo assets/ | RB | 5 | Screenshot in repo proves it runs
[ ] | Schedule next 3 class session topics in shared Google Doc | TK+ML+RB | 10 | Each session has an agenda for the next 6 sessions
[ ] | Each member assigns themselves Sprint 1 tasks in GitHub Issues | TK+ML+RB | 10 | GitHub Issues board populated with Sprint 1 tasks
[ ] | Set up group chat with daily standup (What did, Doing, Blocked) | TK+ML+RB | 5 | Messenger/Viber group created with standup template pinned
⏱ Total estimated time: 205 min (3.4 hrs) ¦ Class session: 90 min · Overflow to Wednesday session

## 📈 Metrics
Success Metrics & KPI Scorecard
Track these every sprint. Review at each retrospective.
KPI | Target | Measurement Method | Sprint Check | Actual | Status
Total programmer hours | 768 hrs | #NAME? | Every sprint | 0 | Not Started
App crash rate (manual QA) | 0 critical crashes | Manual test log spreadsheet | S8 | — | Not Started
PDF export success rate | 100% on 3 test devices | Manual test: 3 devices × 3 templates | S6, S8 | — | Not Started
Screens implemented | ≥ 22 screens | Count .dart files in screens/ | S8 | 0 | Not Started
Unit test coverage (services) | ≥ 80% | flutter test --coverage → lcov report | S8 | 0% | Not Started
Release APK size | < 50 MB | flutter build apk --analyze-size | S8 | — | Not Started
Team velocity consistency | ±10% sprint-to-sprint | #NAME? | Every sprint | — | Not Started
Weekly sprint demos completed | 8 / 8 demos | Demo log in Master Tracker | S8 | 0/8 | Not Started
Android API support range | API 21 → API 34 | Test on 2 physical devices + emulators | S8 | — | Not Started
Capstone Q&A readiness | All 3 members answer any feature Q | Internal rehearsal scoring (1–5) | S8 | — | Not Started
SQLite query performance | All queries < 50 ms | Flutter DevTools → Performance → DB timing | S8 | — | Not Started
UI frame rate | 60 fps on mid-range Android | Flutter DevTools → Performance overlay | S6, S8 | — | Not Started
Zero hardcoded magic numbers | 0 occurrences | Code review checklist + grep search | Every sprint | — | Not Started
Biometric auth optional fallback | 100% fallback to PIN | Manual test: disable biometric → PIN appears | S7 | — | Not Started
DB backup / restore integrity | 100% data intact after restore | Backup → wipe → restore → verify row counts | S7 | — | Not Started
📌 Update the 'Actual' column after every sprint retrospective. Change Status to: In Progress → On Track / At Risk / Failed.