## Sheet1
Task No. | Description | Duration (hours) | Assignee | Prerequisite
Sprint 1 | UI/UX Design and Core System Architecture
DSSBS - 1 | UI/UX Wireframing and Design for Web Admin Dashboard | 3 hrs. | Mary Eleanor Requiez | None
DSSBS - 2 | UI/UX Wireframing and Design for Mobile Feedback Application | 3 hrs. | Mary Eleanor Requiez | None
DSSBS - 3 | Development Environment Setup (XAMPP, Laravel installation, API Base Configuration) | 4 hr. | Sam Loreño | None
DSSBS - 4 | Database Schema Design and Migration Implementation | 6 hrs. | Sam Loreño | DSSBS - 1, DSSBS 2
DSSBS - 5 | Flutter Web Admin Project Initialization and Routing Setup | 5 hrs. | Mary Eleanor Requiez | DSSBS - 1
DSSBS - 6 | Flutter Web Mobile Project Initialization and Navigation Setup | 5 hrs. | Mary Eleanor Requiez | DSSBS - 2
Sprint 2 | Core System Functionalities
DSSBS - 7 | Admin Authentication Module(Register/Login with JWT Implementation | 5 hrs. | Sam Loreño | DSSBS - 3
DSSBS - 8 | Anonymous Feedback Submission API development | 4 hrs. | Sam Loreño | DSSBS - 4
DSSBS - 9 | Integration of Mobile App with feedback submission API | 5 hrs. | Mary Eleanor Requiez | DSSBS - 8
DSSBS - 10 | Integration of Web Admin Login with Authentication API | 5 hrs. | Mary Eleanor Requiez | DSSBS - 7
DSSBS - 11 | Feedback Retrieval API with Filtering and Pagination | 7 hrs. | Sam Loreño | DSSBS - 8
DSSBS - 12 | Admin Dashboard Feedback Viewing Interface | 6 hrs. | Mary Eleanor Requiez | DSSBS - 11
Sprint 3 | AI Integration and Intellegent Processing
DSSBS - 13 | Gemini API Integration for AI Processing | 8 hrs. | Sam Loreño | DSSBS - 8
DSSBS - 14 | Prompt Engineering for Structured Summarization and Sentiment Classification | 6 hrs. | Sam Loreño | DSSBS - 13
DSSBS - 15 | Implementation of AI Result Storage (Summary and Sentiment) | 4 hrs. | Sam Loreño | DSSBS - 12
DSSBS - 16 | Display AI - generated summary in admin dashboard | 4 hrs | Mary Eleanor Requiez | DSSBS - 14
DSSBS - 17 | Sentiment Badge UI | 3 hrs | Mary Eleanor Requiez | DSSBS - 15
DSSBS - 18 | Auto-trigger Analysis after feedback submission | 4 hrs. | Sam Loreño | DSSBS - 12
Sprint 4 | Report Analysis
DSSBS - 19 | SentimentAggregation and Statistical Computation per office | 8 hrs. | Sam Loreño | DSSBS - 15
DSSBS - 20 | Recurring issue detection and keyword frequency analysis | 12 hrs. | Sam Loreño | DSSBS - 15
DSSBS - 21 | Reports and analysis API development | 8 hrs. | Sam Loreño | DSSBS - 18
DSSBS - 22 | Web-based analytics dashboard with charts and visualizations | 10 hrs. | Mary Eleanor Requiez | DSSBS - 20
DSSBS - 23 | Office-level consideration AI summary feature | 4 hrs. | Mary Eleanor Requiez | DSSBS - 16
Sprint 5 | Deployment, Security and Finalization
DSSBS - 24 | API security hardening (input validation, sanitization, rate limiting) | 12 hrs. | Sam Loreño | DSSBS - 11
DSSBS - 25 | Backend development to production environment | 10 hrs. | Sam Loreño | DSSBS - 23
DSSBS - 26 | Web admin application deployment | 8 hrs. | Mary Eleanor Requiez | DSSBS -21
DSSBS - 27 | Mobile application build generation and device testing | 12 hrs. | Mary Eleanor Requiez | DSSBS - 9
DSSBS - 28 | Comprehensive system testing and final bug fixing | 10 hrs. | Sam Loreño | DSSBS - 26